## Evaluation Report
Performance Evaluation Report
EC101 Dr. Beyers Naude Local Municipality
Q3(Jan-March)
Output as per support plan | Output achieved | Allocation as per Support Plan | Allocation spent to date | Allocation still to be spent | Reasons for non achievement of output | Remedial Measures to be implemented | Date when output will be achieved
Establishment of a Budget and Treasury Office (BTO) with positions filled by appropriately qualified personnel |  | 1810000 |  | 1810000
Appointment of atleast 5 interns | Yes | 700000 | 230700.7 | 469299.3
Acquisition, upgrade and maintenance of financial management systems to produce multi- year budgets, in-year reports, Service Delivery and Budget Implementation Plans, Annual Financial Statements, annual reports and automated financial management practices including the municipal Standard Chart of Accounts |  | 750000 | 553573.5 | 196426.5
Support the training of municipal officials in financial management towards attaining the minimum competencies |  | 700000 |  | 700000
Preparation and timely submission of Annual Financial Statements for audits |  | 1000000 | 2140747 | -1140747
Implementation of financial management reforms and address shortcomings identified in the Financial Management Capability Maturity Model (FMCMM) Assessment report |  | 500000 |  | 500000
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| Signature | Date
Municipal Manager
Chief Financial Officer
Note on A3: Select a Quarter from drop down list

## Cash Flow Projection
Dr. Beyers Naude Local Municipality Cash Flow Projection
|  | Quarter 1 |  |  | Q2 |  |  | Q3 |  |  | Q4
Output as per support plan | Allocation still to be spent | July | August | September | October | November | December | January | February | March | April | May | June | Balance Outstanding
Establishment of a Budget and Treasury Office (BTO) with positions filled by appropriately qualified personnel | 1810000 | Quarter 1 July: 0; Quarter 1 August: 0; Quarter 1 September: 0 | 1810000
Appointment of atleast 5 interns | 469299.3 | 31452 | 33768 | 30204 | 23814 | 0 | 23804.43 | 28952.1 | 29486.03 | 29220.18 |  |  |  | 238598.56
Acquisition, upgrade and maintenance of financial management systems to produce multi- year budgets, in-year reports, Service Delivery and Budget Implementation Plans, Annual Financial Statements, annual reports and automated financial management practices including the municipal Standard Chart of Accounts | 196426.5 | 6582 | 22904 | 9690 | 62832 | 169185.45 | 25914.37 | 25622.4 | 92774.54 | 138068.7 |  |  |  | -357146.96
Support the training of municipal officials in financial management towards attaining the minimum competencies | 700000 | Quarter 1 July: 0; Quarter 1 August: 0; Quarter 1 September: 0 | 700000
Preparation and timely submission of Annual Financial Statements for audits | -1140747 | Quarter 1 July: 0; Quarter 1 August: 0; Quarter 1 September: 0; Q3 January: 1641569.63; Q3 February: 82872.02; Q3 March: 416305.7 | -3281494.35
Implementation of financial management reforms and address shortcomings identified in the Financial Management Capability Maturity Model (FMCMM) Assessment report | 500000 | Quarter 1 July: 0; Quarter 1 August: 0; Quarter 1 September: 0 | 500000
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
| Signature | Quarter 1 July: Date
Municipal Manager
Chief Financial Officer