ORGANISATIONAL PERFORMANCE MANAGEMENT

- INTRODUCTION

The function of Performance Management within the municipality is performed in the office of the municipal manager, and includes monitoring the implementation of the Integrated Development Plan (IDP) through the Service Delivery and Budget Implementation Plan (SDBIP).  Legislation states that key performance indicators and targets must be implemented to enable continual monitoring of the municipality and its administration.  These indicators pin point areas of focus for each financial year and are included in the IDP.  Once approved the IDP is married to the budget in a document called the Service Delivery and Budget Implementation Plan (SDBIP) which provides a workable management tool from which to operate under and monitor progress.  The SDBIP is then used to develop agreed performance plans for the Municipal Manager and Directors which is evaluated quarterly.

The Annual Performance Report is hereby submitted to the Dr. Beyers Naudé Local Municipal Council in terms of the Municipal Systems Act (MSA), 32 of 2000, section 46(1) and (2), as well as the MFMA Circular No.11

This report covers the performance information from 01 July 2017 to 30 June 2018 and focuses on the implementation of the Service Delivery Budget and Implementation Plan (SDBIP), in relation to the objectives as encapsulated in the Municipality’s Integrated Development Plan (IDP).

This Report reflects actual performance of the Municipality as measured against the performance indicators and targets in its Integrated Development Plan (IDP) and Service Delivery and Budget Implementation Plan (SDBIP) for 2017/2018.

The format of the report will reflect the Municipality’s Key Performance Indicators (KPI) per Municipal Key Performance Area.  This report will also endeavor to report to Council the Municipality’s performance in terms of the five (5) National Government’s Strategic key Performance Areas for local government, which are (1) Organizational Transformation & Institutional Development ; (2) Service Delivery & Infrastructure Planning; (3) Local Economic Development; (4) Financial Viability and (5) Good Governance and Public Participation.

- LEGISLATIVE REQUIREMENTS

This Annual Performance Report has been compiled in compliance with the requirements of section 46 (1) of the Local Government: Municipal Systems Act, 2000; which stipulates as follows:

- A municipality must prepare for each financial year a performance report reflecting—

(

a)

the performance of the Municipality and each external service pr

` ovider for the

year;

(

b) a comparison of the performance referred to in paragraph (a) with targets set for

performance in the previous financial year; and

(

c) measures taken to improve performance.

Management  Regulations, 2001 states that “A  Municipality’s Performance Management System entails a framework that describes and represents how the municipality’s cycle and processes of performance planning, monitoring, measurement, review, reporting and improvement will be conducted, organized and managed, including determining the roles of the different role players.” Performance management is not only relevant to the organization as a whole, but also  to  the  individuals  employed  in  the  organization  as  well  as  the  external  service providers.  This framework, inter alia, reflects the linkage between the IDP, Budget, SDBIP and Organizational performance.

- PERFORMANCE MANAGEMENT OVERVIEW

In order to improve on performance planning, implementation, reporting and measurement, the institution implemented the following actions;

- Key performance indicators has been reviewed and the SMART principle has been applied, so that there is more effective monitoring and measurement of Key performance indicators.

- The Performance Management Policy that is the guiding tool for the Municipality has been reviewed.

- There is a key performance indicator column added to Capital Budget Projects so that projects are more clearly defined.

- Within the scorecard sent out quarterly for performance evaluations, a column provision has been made for targets not met or lagging behind.

- An automated performance management system is available for use by the Municipality and will be fully utilized in the 2018/2019 financial year.

- The Performance Management is in the process of being cascaded to Management level with in the Municipality and individual performance will be evaluated in the 2018/2019 financial year.

|  | Performance Management guiding policy | All s57/56 Performance contracts signed | Audit Committee | Municipal Public Accounts Committee (MPAC) | Quarterly Performance Reporting to Council | Annual Reporting to Council |
| --- | --- | --- | --- | --- | --- | --- |
| In place? | √ | √ | √ | √ | √ | √ |

Performance Management System Checklist

SERVICE DELIVERY AND BUDGET IMLEMENTATION PLAN OVERVIEW

The organizational performance is evaluated through the Service Delivery Budget Implementation Plan (SDBIP) at departmental levels.

The SDBIP is a plan that converts the IDP and budget into measurable criteria on how, where and when the strategies, objectives and normal business process of the municipality is implemented. It also allocates responsibility to directorates to deliver the services in terms of the IDP and Budget.

The MFMA Circular No.13 prescribes that:

- The IDP and budget must be aligned;

- The budget must address the strategic priorities;

- The SDBIP should indicate what the municipality is going to do during next 12 months; and

- The SDBIP should form the basis for measuring the performance against goals set during the budget /IDP processes.

The SDBIP was prepared as described in the paragraphs below and approved by the Mayor.

The SDBIP consolidate service delivery targets set by Senior Management and provide an overall picture of performance for the municipality as a whole, reflecting performance on its strategic priorities.  Components of the SDBIP include:

One-year detailed plan,

Monthly projections of revenue to be collected for each source;

Expected revenue to be collected NOT billed;

Monthly projections of expenditure (operating and capital) and revenue for each vote;

Quarterly projections of service delivery targets and performance indicators;

Non-financial measurable performance objectives in the form of targets and indicators; and detailed capital project plan broken down by ward.

- PLANNED TARGETS VS ACTUAL RESULTS FOR THE 2017/2018 FINANCIAL YEAR

This section of the Annual Performance Report will report on the Municipality’s actual performance against the planned targets as derived from the Municipality’s SDBIP. Due to the fact that the Municipality has developed (6) Development Priorities, the Dr. Beyers Naudé Local Municipality will report as such.

ORGANISATIONAL PERFORMANCE REPORT AS PER THE SDBIP FOR 2017/2018

- CAPITAL BUDGET PROJECTS - 2017/2018

Infrastructure Development

Number of projects:  10

Number of projects completed/ on target: 10

Number of projects Not on Target: 0

Percentage on targets:  100%

Institutional Development

Number of projects: 21

Number of projects completed/ on target: 9

Number of projects Not on Target: 12

Percentage on targets: 43%

Community Development

Number of projects: 1

Number of projects completed/ on target: 0

Number of projects Not on Target: 1

Percentage on target:  0%

OVERALL

Total Number of Capital Budget Projects per KPA = 32

Number of Key Performance Indicators on Target/Completed = 19

Number of Key Performance Indicators Not on Target = 13

Percentage on Target = 59%

SERVICE DELIVERY TARGETS AND PERFORMANCE INDICATOR- 2017/18

Development Priority:  Infrastructure Development

Number of Indicators: 7

Number of indicators on target: 4

Number of indicators not on target:  3

Percentage on target: 57%

Development Priority:  Community Development

Number of Indicators:  5

Number of indicators on target: 3

Number of indicators not on target:  2

Percentage on target:  60%

Development Priority:  Institutional Development & Organisational Transformation

Number of Indicators:  14

Number of indicators on target: 11

Number of indicators not on target: 3

Percentage on target:  79%

Development Priority:  Local Economic Development

Number of Indicators: 9

Number of indicators on target:  1

Number of indicators not on target: 8

Percentage on target: 11%

Development Priority:  Back to Basics – Good Governance

Number of Indicators: 12

Number of indicators on target: 7

Number of indicators not on target: 5

Percentage on target:  58%

Development Priority:  Back to Basics - Sound Financial Management

Number of Indicators:  11

Number of indicators on target:  8

Number of indicators not on target: 3

Percentage on target:  73%

OVERALL

Total Number of Key Performance Indicators per KPA =   58

Number of Key Performance Indicators on Target/Completed = 34

Number of Key Performance Indicators Not on Target = 24

Percentage on Target = 59%

CAPITAL BUDGET PROJECT ANALYSIS

SDBIP ANALYSIS REPORT – CAPITAL BUDGET PROJECTS - 2017/2018

Infrastructure Development

Number of projects:  10

Number of projects completed/ on target:  10

Number of projects not on target: 0

Percentage on targets: 100%

Total budget per focus area versus expenditure:

| IDP Ref. No. | Project Name & Responsible Person | objective | Strategy | KPI | Previous Years Performance 2016/2017 | Annual Target | Budget R | Expenditure | Expenditure % | On Target/ Not on Target | OVERALL PERFORMANCE 2017/2018 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  | Actual Output | Variance | Reasons for Variance. | Plan of action to address target not reached |
| INFRASTRUCTURE DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 111 | Refurbishment of Borehole Equipment and Installation of Bio- Tower Water Treatment Directorate: Engineering and Planning | To adequately increase bulk water storage, upgrade reticulation systems, secure permanent water supply and properly maintain all infrastructure | Upgrade reticulation system by systematically replacing old installations. | Supply and installation of 1 borehole pump, installation of 1 water meter, installation of 1 package water treatment plant. Installation of 1 MCC panel for the package plant in Jansenville by 30th June 2018. | New KPI | 4 | External MIG 2,131,800 | 2,131,800.00 | 2,131, 800 | On Target | 2 Borehole 3 Meters 1 Package Plant. Project Completed. | None | n/a | n/a |
| 112 | Willowmore Bulk Water Supply – Wilgerkloof Directorate: Engineering and Planning | To adequately increase bulk water storage, upgrade reticulation systems, secure permanent water supply and properly maintain all infrastructure | Upgrade reticulation system by systematically replacing old installations | Construction of uPVC 2100m pipeline in Willowmore by 31 March 2018. | New KPI | 2100m pipeline | External MIG 3,015,610 | 3,015,610.00 | 100% | On Target | Project completed. Completion certificate available. 2150m uPVC pipeline In Willlowmore. | None | n/a | n/a |
| 112 | Willomore Bulk Water Supply – Upgrading, extensions and additional Directorate: Engineering and Planning | To adequately increase bulk water storage, upgrade reticulation systems, secure permanent water supply and properly maintain all infrastructure | Upgrade reticulation system by systematically replacing old installations. | Construction of uPVC 2000m pipeline in Willomore by 30th June 2018. | New KPI | 2000m pipeline | External MIG 3,610,461 | 3,610,461 | 100% | On Target | Project completed. 3100m uPVC pipeline in Willowmore | None | n/a | n/a |
| IDP Ref. No. | Project Name & Responsible Person | Objective | Strategy | KPI | Previous Years Performance 2016/2017 | Annual Target | Budget R | Expenditure | Expenditure % | On Target/ Not on Target | OVERALL PERFORMANCE 2017/2018 |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Actual Output | Variance | Reasons for Variance. | Plan of action to address target not reached |
| 114 | Aberdeen: Upgrading of Bulk Water: Supply Phase 2 Directorate: Engineering and Planning | To adequately increase bulk water storage, upgrade reticulation systems, secure permanent water supply and properly maintain all infrastructure | Upgrade reticulation system by systematically replacing old installations. | Drilling and equipping of 2 boreholes and 1 Hydrological report in Aberdeen by 30th June 2018. | New KPI | 2 boreholes and 1 Hydrological Report | External MIG 1,109,073 | 1,109,073 | 100% | On Target | 5 Boreholes drilled and 1 hydrological report. | None | n/a | n/a |
| 118 | Graaff-Reinet Emergency Water Supply Scheme Directorate: Engineering and Planning | To adequately increase bulk water storage, upgrade reticulation systems, secure permanent water supply and properly maintain all infrastructure | Upgrade reticulation system by systematically replacing old installations. | Construction of 1 steel reservoir and installation of 315mm bulk rising main in Graaff-Reinet by 30th June 2018. | New KPI | 1 Steel Reservoir, 315mm rising main | External RBIG 22,000,000 | 19,605,000 | Funding 100% spent. DW&S reduced funding allocation | On Target | 1 Steel Reservoir, 1 rising main. | Reservoirs plus Pipe Lines Constructed | n/a | n/a |
| IDP Ref. No. | Project Name & Responsible Person | Objective | Strategy | KPI | Previous Years Performance 2016/2017 | Annual Target | Budget R | Expenditure | Expenditure % | On Target/ Not on Target | OVERALL PERFORMANCE 2017/2018 |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Actual Output | Variance | Reasons for Variance. | Plan of action to address target not reached |
| 131 | Graaff-Reinet: Upgrading Solid Waste Site of 2 New Cells Directorate: Community Services | Solid Waste Disposal Sites (Landfills), that are compliant, have adequate capacity and are properly managed and maintained | Systematically upgrade existing infrastructure; replace and rehabilitate where applicable. | Number of cells constructed in Graaff-Reinet Solid Waste Disposal Facility by 30th June 2018. | New KPI | 2 cells | External MIG 675,047 | 675,047 | 100% | On Target | 4 Cells constructed Project Completed. | None | n/a | n/a |
| 141 | Upgrade Infrastructure Directorate: Engineering and Planning | To adequately upgrade the electrical supply and install the necessary electrical infrastructure, as well as regular maintenance thereof | Conduct an audit of electrification needs and infrastructure in the Dr Beyers Naudé LM. | Installation of 1.8KM overhead powerlines in Graaff-Reinet AND Electrification of 64 RDP Houses in Willowmore by 30th June 2018. | New KPI | 1.8km powerline AND 64 RDP houses electrified | External DOE 7,000,000 | 7,000,000.00 | 100% | On Target | Project completed. Close-out report available. 1.8km powerline Electrification of 64 RDP Houses | none | n/a | n/a |
| IDP Ref. No. | Project Name & Responsible Person | Objective | Strategy | KPI | Previous Years Performance 2016/2017 | Annual Target | Budget R | Expenditure | Expenditure % | On Target/ Not on Target | OVERALL PERFORMANCE 2017/2018 |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Actual Output | Variance | Reasons for Variance. | Plan of action to address target not reached |
| 147 | Transformers Directorate: Engineering and Planning | To adequately upgrade the electrical supply and install the necessary electrical infrastructure, as well as regular maintenance thereof | Conduct an audit of electrification needs and infrastructure in the Dr Beyers Naudé LM. | Number of Standby Transformers Purchased by 30th June 2018. | New KPI | 1 | Internal 336,120 | 336,120 | 100% | On Target | Project completed. 7 transformers purchased. | + 6 | More Transformers purchased based on need. | n/a |
| 163 | Jansenville /Klipplaat roads and storm water drainage Rehabilitation Directorate: Engineering and Planning | To adequately construct, upgrade or install Streets & Stormwater networks and to maintain them on a regular basis | Systematically upgrade existing infrastructure; replace and rehabilitate where applicable | Paving of 1500m2 roads in Jansenville and 1500m2 roads in Klipplaat by 30th June 2018. | New KPI | 3000m2 of road paved | External MIG 2,724,871 | 2,724,871 | 100% | On Target | 3600m2 Constructed Project completed. Completion certificate available. | None | n/a | n/a |
| IDP Ref. No. | Project Name & Responsible Person | Objective | Strategy | KPI | Previous Years Performance 2016/2017 | Annual Target | Budget R | Expenditure | Expenditure % | On Target/ Not on Target | OVERALL PERFORMANCE 2017/2018 |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Actual Output | Variance | Reasons for Variance. | Plan of action to address target not reached |
| 163 | Graaff Reinet roads and storm water drainage Rehabilitation Directorate: Engineering and Planning | To adequately construct, upgrade or install Streets & Stormwater networks and to maintain them on a regular basis | Systematically upgrade existing infrastructure; replace and rehabilitate where applicable | Construction of a 4500m3 berm and progress report by 30th June 2018. | New KPI | 4500m3 berm and progress report. | External MIG 5,555,489 | 5,555,489 | 100% | On Target | Project completed. 11,376m3 berm constructed and progress report. | 6876 m3 | n/a | n/a |
| IDP Ref. No. | Project Name & Responsible Person | Objective | Strategy | KPI | Previous Years Performance 2016/2017 | Annual Target | Budget R | Expenditure | Expenditure % | On Target/ Not on Target | OVERALL PERFORMANCE 2017/2018 |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Actual Output | Variance | Reasons for Variance. | Plan of action to address target not reached |
| COMMUNITY DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 201 | Graaff-Reinet: Development of a Soccerfield in Kroonvale, phase 2 Directorate: Community Services | Solid Waste Disposal Sites (Landfills), that are compliant, have adequate capacity and are properly managed and maintained | Systematically upgrade existing infrastructure; replace and rehabilitate where applicable. | Construction of one 130m2 ablution facility at the Kroonvale soccerfield by 30th June 2018 | New KPI | 130m2 ablution facility. And progress report. | External MIG 1,034,649 | 1,034,649 | 100% | Not on Target | Service provider appointed. | 130m2 ablution facility. And progress report. | Project phased over two financial years. | Project phased over two financial years. Construction to commence in 2018/19. |

Institutional Development

Number of projects: 21

Number of projects completed/ on target:  8

Number of projects not on target: 13

Percentage on targets:  38%

Total budget per focus area versus expenditure:

| IDP Ref. No. | Project Name & Responsible Person | objective | Strategy | KPI | Previous Years Performance 2016/2017 | Annual Target | Budget R | Expenditure | Expenditure % | On Target/ Not on Target | OVERALL PERFORMANCE 2017/2018 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  | Actual Output | Variance | Reasons for Variance. | Plan of action to address target not reached |
| INSTITUTIONAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 317 | VEHICLES Directorate: Community Services | To improve service delivery by replacing the current fleet with more reliable vehicles. | Purchase vehicles or plant required for delivering the necessary services. | Number of Refuse trucks purchased by 30th June 2018 | New KPI | 2 refuse trucks | External SBDM 1,000,000 | 0.00 | 0% | Not on Target | Trucks adjudicated. | 2 | Delay in SCM processes. | Trucks adjudicated and will be delivered by the end of September 2018. |
| 330 | Air Conditioners Directorate: Budget & Treasury | To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant | Equip offices and areas of service delivery with adequate resources. | Number of Air conditioners purchased by 30 September 2017. | No Air conditioners Purchased. | 2 | External FMG 20,000 | 12,800 | 64% | On Target | 6 air conditioners installed | +4 | More Air conditioners needed. | n/a |
| IDP Ref. No. | Project Name & Responsible Person | objective | Strategy | KPI | Previous Years Performance 2016/2017 | Annual Target | Budget R | Expenditure | Expenditure % | On Target/ Not on Target | OVERALL PERFORMANCE 2017/2018 |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Actual Output | Variance | Reasons for Variance. | Plan of action to address target not reached |
| 330 | Air Conditioners | To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant | Equip offices and areas of service delivery with adequate resources. | Number of Air conditioners purchased by 30 September 2017. | No Air conditioners Purchased. | 6 | Internal 60,000 | 0 | 0% | Not on Target | No output | 6 | Cash flow constraints | n/a |
| 330 | Air Conditioners Directorate: MM/Internal Audit | To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant | Equip offices and areas of service delivery with adequate resources. | Number of air conditioners purchased by 30th June 2018. | No Air conditioners Purchased. | 1 | External FMG 15,000 | 0 | 0% | Not on Target | No air conditioner purchased. | 1 | This did not form part of the FMG business plan. Cash flow Constraints | n/a |
| 330 | Air Conditioners Directorate: Corporate Services | To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant | Equip offices and areas of service delivery with adequate resources. | Number of air conditioners purchased by 30th June 2018. | No Air conditioners Purchased. | 1 | External MDTG NT 15,000 | 0 | 0% | Not on Target | No Output | 1 | n/a | n/a |
| 331 | Office Furniture Directorate: Budget & Treasury | To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant | Equip offices and areas of service delivery with adequate resources. | Purchase 4 Cabinets, 3 Shelves, 14 Tables, and 21 Chairs by 31 December 2017. | New KPI | 42 | External FMG 150,000 | 28,899 | 19% | Not on Target | 1 desk, 4 chairs on order. | 37 furniture items | This did not form part of the FMG business plan. Cash flow constraints. | n/a |
| 331 | Office Furniture Directorate: MM/Internal Audit | To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant | Equip offices and areas of service delivery with adequate resources. | Purchase 2 desks by 30th June 2018 |  | 2 | External FMG 22,000 | 11, 431.99 | 52% | On Target | 1 Desk, 1 Shelf, 2 visitor chairs and 1 high back chair. | 1 shelf, 2 visitor chairs and 1 high back chair. | n/a | n/a |
| IDP Ref. No. | Project Name & Responsible Person | objective | Strategy | KPI | Previous Years Performance 2016/2017 | Annual Target | Budget R | Expenditure | Expenditure % | On Target/ Not on Target | OVERALL PERFORMANCE 2017/2018 |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Actual Output | Variance | Reasons for Variance. | Plan of action to address target not reached |
| 334 | Cleaning Appliances Directorate: Budget & Treasury | To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant | Equip offices and areas of service delivery with adequate resources. | Number of Polishers and Vacuum cleaners to be purchased by 30th September 2017. | New KPI | 2 | External FMG 30,000 | 30, 000 | 100% | On Target | Purchased 1 Polisher, 1 Vacuum cleaner and 1 Micro-wave. | 1 Micro - wave | Additional requirement | n/a |
| 341 | Tools and Equipment Directorate: Community Services/ Protection Service | To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant | Equip offices and areas of service delivery with adequate resources. | Number of Specialised Occupational Health and Safety (Fire) equipment purchased by 31 December 2017. | No equipment purchased | 14 | Internal/ External 50,000 | 0 | 0% | Not On Target | Supply and delivery of 16 Fire bunker suits during the 4th quarter. | +2 | Additional Safety (fire) equipment needed, Target date of 31 December was not achieved. | n/a |
| IDP Ref. No. | Project Name & Responsible Person | Objective | Strategy | KPI | Previous Years Performance 2016/2017 | Annual Target | Budget R | Expenditure | Expenditure % | On Target/ Not on Target | OVERALL PERFORMANCE 2017/2018 |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Actual Output | Variance | Reasons for Variance. | Plan of action to address target not reached |
| 342 | Tools and Equipment Directorate: Budget & Treasury | To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant | Equip offices and areas of service delivery with adequate resources. | Number of Hand – Held devices purchased for meter reading throughout the Dr. Beyer’s Naude Local Municipality 31 December 2017. | No hand held devices purchased. | 4 | External FMG 70,000 | 0 | 0% | Not on Target | No hand-held devices purchased for 2017/2018 | 4 | n/a | No funding available. This was not included in the business plan for FMG. Cash flow constraints |
| IDP Ref. No. | Project Name & Responsible Person | Objective | Strategy | KPI | Previous Years Performance 2016/2017 | Annual Target | Budget R | Expenditure | Expenditure % | On Target/ Not on Target | OVERALL PERFORMANCE 2017/2018 |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Actual Output | Variance | Reasons for Variance. | Plan of action to address target not reached |
| 345 | Machinery Office, e.g. shredders Directorate: MM/ Internal Audit | To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant. | Equip offices and areas of service delivery with adequate resources. | Purchase a shredder and overhead projector by 30th June 2018 | New KPI | 2 | External FMG 9000 | 3,772.00 | 42% | Not on Target | Shredder purchased. | 1 overhead projector. | To be purchased in next financial year. | To be purchased in next financial year |
| IDP Ref. No. | Project Name & Responsible Person | objective | Strategy | KPI | Previous Years Performance 2016/2017 | Annual Target | Budget R | Expenditure | Expenditure % | On Target/ Not on Target | OVERALL PERFORMANCE 2017/2018 |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Actual Output | Variance | Reasons for Variance. | Plan of action to address target not reached |
| 351 | IT Software Directorate: Corporate Services | To improve overall efficiency of ICT ~ administration, billing, record keeping, information sharing and communication; to ensure optimal, cost-effective production and quality service delivery | Conduct a comprehensive ICT audit. | Number of Exchange Hosted mailboxes purchased By 31 September 2017. | New KPI | 10 | External FMG 70,000 | 0 | 0% | On Target | 37 Exchange hosted mailboxes purchased in the 1st quarter. | 17 | n/a | n/a |
| 351 | IT Software Directorate: Corporate Services | To improve overall efficiency of ICT ~ administration, billing, record keeping, information sharing and communication; to ensure optimal, cost-effective production and quality service delivery | Conduct a comprehensive ICT audit. | Number of Windows pro licenses purchased by 31 September 2017. | New KPI | 10 | External FMG 40,000 | 0 | 0% | On Target | 37 Windows pro licenses purchased during the 1st quarter. | 17 | n/a | n/a |
| 351 | IT Software Directorate: Corporate Services | To improve overall efficiency of ICT ~ administration, billing, record keeping, information sharing and communication; to ensure optimal, cost-effective production and quality service delivery | Conduct a comprehensive ICT audit. | Number of Microsoft Office H&B Licences purchased by 31 September 2017. | New KPI | 10 | External FMG 50,000 | 0 | 0% | On Target | 37 Microsoft Office H&B Licences purchased in the 1st quarter. | 17 | n/a | n/a |
| 351 | IT Software Directorate: MM/ Internal Audit | To improve overall efficiency of ICT ~ administration, billing, record keeping, information sharing and communication; to ensure optimal, cost-effective production and quality service delivery | Identify and Implement suitable projects | Installation of Internal audit software by 30th June 2018 | New KPI | Software installed. | External FMG 200,000 | 0 | 0% | Not on Target | Supply chain processes not finalized. | Software | n/a | n/a |
| 352 | IT Hardware Directorate: Corporate Services | To improve overall efficiency of ICT ~ administration, billing, record keeping, information sharing and communication; to ensure optimal, cost-effective production and quality service delivery | Conduct a comprehensive ICT audit. | Purchased 1 drill, 2 step ladder, 1 glue gun, 1 crimping tool, 1 network tester) by 31 December 2017. | New KPI | 6 | External FMG 10,000 | 0 | 0% | Not on Target | No Output | 6 | n/a | n/a |
| IDP Ref. No. | Project Name & Responsible Person | objective | Strategy | KPI | Previous Years Performance 2016/2017 | Annual Target | Budget R | Expenditure | Expenditure % | On Target/ Not on Target | OVERALL PERFORMANCE 2017/2018 |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Actual Output | Variance | Reasons for Variance. | Plan of action to address target not reached |
| 352 | IT Hardware Directorate: Corporate Services | To improve overall efficiency of ICT ~ administration, billing, record keeping, information sharing and communication; to ensure optimal, cost-effective production and quality service delivery | Conduct a comprehensive ICT audit. | Number of PC/Laptops purchased by the 31st December 2017. | No computers Purchased | 10 | External Amalgamation Grant 250,000 | 237,548.00 | 95% | On Target | 37 Laptops purchased during the 1st quarter. | 27 | Laptops Purchased for Councillors | n/a |
| 352 | IT Hardware Directorate: Corporate Services | To improve overall efficiency of ICT ~ administration, billing, record keeping, information sharing and communication; to ensure optimal, cost-effective production and quality service delivery. | Conduct a comprehensive ICT audit. | Number of Computers purchased by the 30th June 2018. | No computers Purchased | 3 | External MDTG NT 44,000 | 102,983.00 | 100% | On Target | 10 Laptops purchased for finance staff. | 7 | Tools of trade required. | n/a |
| IDP Ref. No. | Project Name & Responsible Person | objective | Strategy | KPI | Previous Years Performance 2016/2017 | Annual Target | Budget R | Expenditure | Expenditure % | On Target/ Not on Target | OVERALL PERFORMANCE 2017/2018 |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Actual Output | Variance | Reasons for Variance. | Plan of action to address target not reached |
| 353 | IT Infrastructure Directorate: Corporate Services | To improve overall efficiency of ICT ~ administration, billing, record keeping, information sharing and communication; to ensure optimal, cost-effective production and quality service delivery | Identify areas in need of systems upgrade and formulate appropriate ICT Plan & Policies (including IT Disaster Recovery). | Number of Municipal Buildings identified for the Installation of WIFI by 30th June 2018. | New KPI | 4 | External FMG 200,000 | 0 | 0% | Not on Target | No output | n/a | n/a | ICT assessment conducted during the 4th quarter |
| 354 | Electronic Systems Directorate: Budget & Treasury | To improve overall efficiency of ICT ~ administration, billing, record keeping, information sharing and communication; to ensure optimal, cost-effective production and quality service delivery | Conduct a comprehensive ICT audit. | Number of Vending Machines purchased by 31 December 2017. | No vending machines purchased. | 4 | External FMG 220,000 | 0 | 0% | Not on Target | Tender for prepaid vending system adjudicated. | n/a | n/a | New vending points to be implemented with new projects in 2018/2019 financial year. |
| IDP Ref. No. | Project Name & Responsible Person | objective | Strategy | KPI | Previous Years Performance 2016/2017 | Annual Target | Budget R | Expenditure | Expenditure % | On Target/ Not on Target | OVERALL PERFORMANCE 2017/2018 |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Actual Output | Variance | Reasons for Variance. | Plan of action to address target not reached |
| 354 | Electronic Systems Directorate: MM/ Communications | To improve overall efficiency of ICT ~ administration, billing, record keeping, information sharing and communication; to ensure optimal, cost-effective production and quality service delivery. | Conduct a comprehensive ICT audit. | Number of Loudhailers purchased by 30th June 2018. | New KPI | 8 | External MDTG EC 9,600 | 9600 | 100% | On Target | Loudhailers procured. Awaiting delivery | none | n/a | n/a |

SERVICE DELIVERY TARGETS AND PERFORMANCE INDICATORS PERFORMANCE ANALYSIS

- SERVICE DELIVERY TARGETS AND PERFORMANCE INDICATORS

| DEVELOPMENT PRIORITY - INFRASTRUCTURE DEVELOPMENT |  |  |  |  |  | Overall Performance |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective | Strategy | Depart | KPI | Previous Years Performance 2016/2017 | Annual Target | On Target/ Not on Target | Brief Description of Actual Output | Variance | Reasons for Variance | Brief Plan of Action to address KPI Target not achieved. |
| To adequately increase bulk water storage, upgrade reticulation systems, secure permanent water supply and properly maintain all infrastructure. | Identify and implement suitable Projects. | Engineering and Planning | Number of reservoirs cleaned in Graaff-Reinet by 30th June 2018. | 7 Reservoirs were cleaned. | 6 | On Target | 8 cleaned | +1 | 1 additional reservoir cleaned. | n/a |
| For all households to have uninterrupted access to good quality, potable water. | Implement Action Plans contained in WSDP and ensure that proper controls and monitoring measures are in place | Engineering and Planning | Monitor water quality through taking 13 Samples per month. | 156 samples taken | 156 | On Target | 222 samples | +66 | More samples taken to ensure quality water. | n/a |
| For all households to have uninterrupted access to good quality, potable water. | Implement Action Plans contained in WSDP and ensure that proper controls and monitoring measures are in place | Engineering and Planning | Percentage compliance with drinking water quality standards (micro-bacterialogical) quarterly. | 88% Compliance with drinking water quality | 80% | On Target | 99.9% | 19.9% | n/a | n/a |
| To adequately upgrade the electrical supply and install the necessary electrical infrastructure, as well as regular maintenance thereof. | Identify and implement suitable Electrification Projects | Engineering and Planning (Electrical Department | Number of oil test sample reports for a Transformer by 30 June. 2018. | 21 | 1 | On Target | 1 test sample report. | None | n/a | n/a |
| Effective recycling programmes that will reduce waste volumes at landfill site and create economic opportunities for the Community | Step up educational campaigns to encourage all citizens to take pride in their areas and keep them clean; to recycle at source | Community Services | Number of Waste management Campaigns held at ward meetings, schools and other institutions by 30th June 2018. | New KPI | 12 | Not On Target | No waste management campaigns held. Waste management campaign scheduled for the 18th July 2018. | 12 | n/a | Waste management campaign scheduled for the 18th July 2018. |
| The eradication of illegal dumping and littering and creation of clean and healthy urban areas and surrounding environment | Provide adequate waste disposal facilities and containers, as well as regular waste removal service | Community Services | Number of quarterly reports on Cleaning of illegal dumping sites and waste skips by 30th June 2018. | New KPI | 4 | Not on Target | No output | 12 | n/a | Regular reporting to community service standing committee to commence in the 2018/19 financial year. |
| The eradication of illegal dumping and littering and creation of clean and healthy urban areas and surrounding environment | Provide adequate waste disposal facilities and containers, as well as regular waste removal service | Community Services | Number of reports on cleaning parks and all recreational areas by 30th June 2018. | New KPI | 4 | Not on Target | No output | 12 | n/a | Regular reporting to community service standing committee to commence in the 2018/19 financial year. |
| DEVELOPMENT PRIORITY - COMMUNITY DEVELOPMENT |  |  |  |  |  | Overall Performance |  |  |  |  |
| Objective | Strategy | Depart | KPI | Previous Years Performance 2016/2017 | Annual Target | On Target/ Not on Target | Brief Description of Actual Output | Variance | Reasons for Variance | Brief Plan of Action to address KPI Target not achieved. |
| To significantly reduce and mitigate the negative impact of disasters and to upgrade road traffic and pedestrian safety, with regular maintenance on installations and infrastructure as an ongoing concern. | Regularly review and update the Municipality’s Disaster Management Plan and ensure that it incorporates threats identified throughout the region | Protection Services Department | Review 1 Disaster management plan and approve by council by 30th June 2018 | Not On Target Aurecon have been appointed by SBDM to compile a risk assessment in respect of all disasters in the DBNLM and the assessment is not completed yet. Awaiting completion report from Aurecon. | 1 | Not on Target | No Output | 1 | Due to Aurecon that was appointed by SBDM to compile a risk assessment the Disaster management plan was not reviewed. | The information from the risk assessment after completed will be used to review the Disaster management plan in the 2018/19 FY |
| To fully involve, capacitate and empower the SPU Sector, with special focus on the Disabled, Youth and Women. | Design programmes and arrange events that will encourage the participation of the SPU sector, especially the Disabled, Youth and Women | Municipal Manager/ SPU unit | Monitor 9 Sports & Cultural events Organized for the Community through reports submitted by SPU Officer to the Office of the Municipal Manager by 30th June 2018 | World Aids Day 01-11 December 2016 Reconciliation Day – 16 December 2016 Launch of the Athletics League – 29 October 2016 Camdeboo Clashes – 7 September 2016 Opening of Festive Season – 11 December 2016 16 Days of Activism Against Women and Child Abuse – 25 November 2016 – 10 December 2016 EPA Brutal Fruit Netball League – 01 October 2016 Let’s Play MNET & SuperSport Championship | 9 | On Target | National Day for disabled persons, World Aids Day, Reconciliation Day, 16 Days of Activism Against Women and Child Abuse, Opening of Festive Season, Crime Awareness and Human Rights Day Commemorations in collaboration with SAPS and other Stakeholders, Showville Talent Search in Commemoration of Human Rights Month in collaboration with SABC 2 and Okuhle Productions and Freedom Day Commemorations Tournament. | None | n/a | n/a |
| To fully involve, capacitate and empower the SPU Sector, with special focus on the Disabled, Youth and Women. | Design programmes and arrange events that will encourage the participation of the SPU sector, especially the Disabled, Youth and Women. | Municipal Manager/ SPU Unit | Number of SPU Consultative Forums established, namely: Youth Council, Local Sports Council, Local Aids Council, Women’s Forum and Disabled Forum by 31 December 2017. | Local Sports Council Elections – 19 May 2017 Local Aids Council Inductions – 21-22 June 2017 Establishment of Women’s Caucus – 25 April 2017 Establishment of the Initiation Forum – 7 June 2017 The election of a Youth Council and Disabled forum will commence in the new financial year. | 4 | Not on Target | All councils established except youth council. Youth council not established, however provision is made for the establishment of the council in 2018/19. | 1 council | Due to vast area no youth council established. | Youth council not established, however provision is made for the establishment of the council in 2018/19. |
| To fully involve, capacitate and empower the SPU Sector, with special focus on the Disabled, Youth | Design programmes and arrange events that will encourage the participation of the SPU sector, especially the Disabled, Youth and Women. | Municipal Manager/ SPU Unit | Monitor effectiveness of SPU consultative councils/ Forums by providing quarterly reports to the office of the Municipal Manager. | New KPI | 4 | On Target | Quarterly reports submitted | none | n/a | n/a |
| To fully involve, capacitate and empower the SPU Sector, with special focus on the Disabled, Youth | Design programmes and arrange events that will encourage the participation of the SPU sector, especially the Disabled, Youth and Women. | Municipal Manager/ SPU Unit | Number of training programmes for vulnerable groups especially youth and disabled citizens by 30th June 2018. | Computer Training for Youth – July 2016 – June 2017 56 students trained every month on basic computer training. | 8 | On Target | Arts and Crafts Training throughout BNLM Computer training in Willomore/ Steytlervile/ Rietbron through the year. Additional Training programmes implemented: Mass Participation Programme in partnership with Environmental Affairs: Horticulture Training and Painting Training. Human Settlements, NHBRC, NYDA and BNLM: Women’s Build programme SA Army, OTP, SBDM and BNLM: Maintenance and Infrastructure Training Programme. AGRI SETA and BNLM: AET Training in Klipplaat and Graaff-Reinet. Media works and BNLM: Work readiness training | n/a | n/a | n/a |
| DEVELOPMENT PRIORITY – ORGANISATIONAL TRANSFORMATION & INSTITUTIONAL DEVELOPMENT |  |  |  |  |  | OVERALL PERFORMANCE |  |  |  |  |
| Objective | Strategy | Depart | KPI | Previous Years Performance 2016/2017 | Annual Target | On Target/ Not on Target | Brief Description of Actual Output | Variance | Reasons for Variance | Brief Plan of Action to address KPI Target not achieved. |
| To recruit staff with adequate qualifications, skills, training and experience. | Finalise the review of the Staff Establishment as a matter of urgency | Corporate services (Human resource department) | Develop an organizational structure by 31 December 2017. | Macro structure for Beyers Naude Local Municipality adopted by Council. A consulted was appointed to develop an organizational structure for the municipality. The Macro structure was tabled and approved by Council, the Micro structure to be finalized. | 1 | On Target | The organizational structure was approved on 20 September 2017. Management is currently engaged with the placement of staff. | none | n/a | n/a |
| To recruit staff with adequate qualifications, skills, training and experience. | Finalise the review of the Staff Establishment as a matter of urgency | Corporate services (Human resource department) | Number of Delegation registers developed by 31 December 2017 | New KPI | 1 | On Target | 1 Delegation Register has been approved by Council and is currently reviewed by the Service Provider to include sub-delegations. | none | n/a | n/a |
| To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as legally compliant | Implement Plan & Policies and upgrade systems accordingly; provide suitable training to enable staff to utilize these systems optimally and correctly. | Corporate services (Human resource department) | Number of employment equity plans developed by 31 December 2017. | Not On Target Organogram process delaying the development of an employment equity plan. | 1 | Not On Target | Task team appointed for compiling of Employment Equity Plan. Plan can only be developed after placement is finalized. | 1 | Deregistration can only be done after submitting reports for 2017. The opportunity to do the deregistration is August 2018 | Process of deregistration July 2017. Letter written to Dept of Labour. In December different Municipalities reported differently. Deregistration can only be done after submitting reports for 2017. The opportunity to do the deregistration is August 2018 |
| To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant. | Implement Plan & Policies and upgrade systems accordingly; provide suitable training to enable staff to utilize these systems optimally and correctly. | Corporate services (Human resource department) | Develop a workplace skills plan with an annual training report by 30th March 2018 | New KPI | 1 | On Target | WSP was submitted to LGSETA on the 30 April 2018 | none | n/a | n/a |
| To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant. | Implement Plan & Policies and upgrade systems accordingly; provide suitable training to enable staff to utilize these systems optimally and correctly. | Budget and Treasury | Review 13 Financial Policies and table before Council for approval by 30 June 2018. | On Target 10 policies reviewed | 13 | On Target | 14 Financial policies reviewed and approved by Council as well as 2(two) By- Laws. | +1 | n/a | n/a |
| To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant. | Implement Plan & Policies and upgrade systems accordingly; provide suitable training to enable staff to utilize these systems optimally and correctly. | Corporate services (Human resource department) | Number of HR policies reviewed and approved by council by 31st December 2017. | New KPI | 10 | Not on Target | HR Policies reviewed by service provider. Workshop to commence and approval by Council. | 10 | Service provider revising all policies. | Workshop to commence and approval by Council. |
| To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant. | Implement Plan & Policies and upgrade systems accordingly; provide suitable training to enable staff to utilize these systems optimally and correctly. | Engineering and Planning (Town Planning) | Number of SPAZA Shop policies reviewed and approved by council by 31 December 2017. | New KPI | 1 | Not on Target | Policy to be workshopped with council. | 1 | n/a | To commence In the 2018/19 financial year. |
| To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant. | Implement Plan & Policies and upgrade systems accordingly; provide suitable training to enable staff to utilize these systems optimally and correctly. | Budget and Treasury (Supply Chain Department) | Prepare Supply Chain Management Implementation Compliance through 3 quarterly reports by 30 June 2018. | 4 quarterly reports to Council. | 3 | On Target | Three (3) monthly reports and 1 quarterly report. | None | n/a | n/a |
| To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant. | Implement Plan & Policies and upgrade systems accordingly; provide suitable training to enable staff to utilize these systems optimally and correctly. | Budget and Treasury (Supply Chain Department) | Conduct quarterly Assets reconciliation between AR and GL. 4 quarterly reports by 30 June 2018. | 4 quarterly reports and the use of EQMS Consultants | 3 | On Target | Quarterly reconciliations performed | None | n/a | n/a |
| To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant. | Implement Plan & Policies and upgrade systems accordingly; provide suitable training to enable staff to utilize these systems optimally and correctly. | Budget and Treasury (Supply Chain Department) | Develop and Monitor Contract register for all service providers and provide quarterly reports. | Monthly performance monitoring | 3 | On Target | Quarterly Reports compiled | None | n/a | n/a |
| To develop a performance management culture within the Municipality | Quarterly institutional performance reports to Council. | Municipal Manager/ PMS Unit | 4 quarterly SDBIP Performance reports submitted to Council by 30 June 2018, to inform Council of Institutional Performance. | Quarter 1 and mid-year performance reports were submitted to Council. No performance agreements and plans, delay in performance information submissions. Performance agreements will be entered into for the new financial year and performance plans will be developed for senior managers. The quarterly performance reports will be tabled to council based on the implementation of the performance plans and SDBIP. | 4 | On Target | 4 quarterly SDBIP performance reports was submitted to EXCO and Council during 2017/2018. | none | n/a | n/a |
| To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant. | Implement Plan & Policies and upgrade systems accordingly; provide suitable training to enable staff to utilize these systems optimally and correctly | Corporate Services (Administration Department | Monitor Council resolutions by providing reports on the implementation of council resolutions. | A resolution register template has been approved by Council. Resolutions are recorded and implementation thereof will be reported to Council quarterly in the new financial year. | 4 | On Target | Resolution Register tabled before Council on 28 June 2018. | none | n/a | n/a |
| To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant. | Implement Plan & Policies and upgrade systems accordingly; provide suitable training to enable staff to utilize these systems optimally and correctly. | Corporate Services (Administration Department | Compile a Lease Register with a list of all signed lease agreements by 30 June 2018. | A list was sent to Council on leases, however all expired lease agreements will have to be re advertised. | 1 | On Target | Lease register updated. Lease Register was tabled at the Corporate Services Committee meeting on 12 June 2018, 20 June EXCO and Council on 28 June but was referred back to EXCO. EXCO is scheduled for 26th July 2018. | None | n/a | n/a |
| To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant. | Implement Plan & Policies and upgrade systems accordingly; provide suitable training to enable staff to utilize these systems optimally and correctly. | Corporate Services (Human Resource Department | Report on all disciplinary hearings on a quarterly basis to EXCO. | All disciplinary hearings recorded and reported on a quarterly basis to EXCO. | 4 | On Target | Quarterly reports submitted to EXCO on disciplinary hearings. | None | n/a | n/a |
| DEVELOPMENT PRIORITY – LOCAL ECONOMIC DEVELOPMENT |  |  |  |  |  | OVERALL PERFORMANCE |  |  |  |  |
| Objective | Strategy | Depart | KPI | Previous Years Performance 2016/2017 | Annual Target | On Target/Not on Target | Brief Description of Actual Output | Variance | Reasons for Variance | Brief Plan of Action to address KPI Target not achieved. |
| SUSTAINABLE JOB CREATION  BEE & PARTNERSHIPS  SMME, INDUSTRIAL AND SECTOR DEVELOPMENT  SKILLS DEVELOP-MENT  MAINSTREAMING OF 2ND ECONOMY, YOUTH, DISABLED & WOMEN | Support, encourage and facilitate value-adding initiatives, programmes and projects | Municipal Manager (LED Unit) | Profiling and building capacity in SMMEs – 4 new SMMEs trained in (Export and Business Training) in Graaff-Reinet by 30 June 2017. | 32 SMME’s Trained | 4 | Not on Target | No output | 4 | No SMME’s trained. | Training scheduled for July 2018. |
| SUSTAINABLE JOB CREATION  BEE & PARTNERSHIPS  SMME, INDUSTRIAL AND SECTOR DEVELOPMENT  SKILLS DEVELOP-MENT  MAINSTREAMING OF 2ND ECONOMY, YOUTH, DISABLED & WOMEN | Support, encourage and facilitate value-adding initiatives, programmes and projects | Municipal Manager (LED Unit) | Number of people employed through the EPWP Labour intensive programme to address high unemployment rate in Dr. Beyers Naude Local Municipality by 30 June 2018. | 327 people employed through CWP and 286 employed through EPWP 613 people employed | 200 | On Target | 239 employed , funded by MIG 159 Employed, Founteinbos project | 198 | More employment occurred. | n/a |
| SUSTAINABLE JOB CREATION  BEE & PARTNERSHIPS  SMME, INDUSTRIAL AND SECTOR DEVELOPMENT  SKILLS DEVELOP-MENT  MAINSTREAMING OF 2ND ECONOMY, YOUTH, DISABLED & WOMEN | Support, encourage and facilitate value-adding initiatives, programmes and projects | Municipal Manager (LED Unit) | Number of labourers employed for the project: Reconstruction of Lincom and Asherville schools In Graaff-Reinet by 30 June 2018. | New KPI | 100 | Not On Target | 41 Appointed at Lincom. 11 Appointed at Asherville | 48 | More appointments will be made as these projects progress. | n/a |
| SUSTAINABLE JOB CREATION  BEE & PARTNERSHIPS  SMME, INDUSTRIAL AND SECTOR DEVELOPMENT  SKILLS DEVELOP-MENT  MAINSTREAMING OF 2ND ECONOMY, YOUTH, DISABLED & WOMEN | Support, encourage and facilitate value-adding initiatives, programmes and projects | Municipal Manager (LED Unit) | Number of SMME’s employed for the project: Reconstruction of Lincom and Asherville schools In Graaff-Reinet by 30 June 2018 | New KPI | 16 | Not on Target | No output | 16 | No SMMEs appointed. | Both projects are lagging and appointments of SMMEs will start in Aug 2018 only. |
| SUSTAINABLE JOB CREATION  BEE & PARTNERSHIPS  SMME, INDUSTRIAL AND SECTOR DEVELOPMENT  SKILLS DEVELOP-MENT  MAINSTREAMING OF 2ND ECONOMY, YOUTH, DISABLED & WOMEN | Develop LED Strategic Plan with an economic Vision for the Municipality. | Municipal Manager (LED Unit) | Number of commonage plans developed by the 30th June 2018. | New KPI | 1 | Not on Target | No funding available for the development of a commonage plan. Funding to be sourced | 1 | No funding available for the development of a commonage plan. | No funding to appoint a service provider. The Cogta District Multi-Disciplinary Team committed during a meeting held on 20 July 2018 to assist the municipality developing a Commonage Management Plan. |
| SUSTAINABLE JOB CREATION  BEE & PARTNERSHIPS  SMME, INDUSTRIAL AND SECTOR DEVELOPMENT  SKILLS DEVELOP-MENT  MAINSTREAMING OF 2ND ECONOMY, YOUTH, DISABLED & WOMEN | Support, encourage and facilitate value-adding initiatives, programmes and projects | Municipal Manager (LED Unit) | Assistance and development of SMME’s by 30 June 2018. | New KPI | 5 | Not On Target | Proposal received from SMME’s that require assistance. An evaluation committee to be established | 5 | n/a | An evaluation committee to be established. |
| SUSTAINABLE JOB CREATION  BEE & PARTNERSHIPS  SMME, INDUSTRIAL AND SECTOR DEVELOPMENT  SKILLS DEVELOP-MENT  MAINSTREAMING OF 2ND ECONOMY, YOUTH, DISABLED & WOMEN | Develop LED Strategic Plan with an economic Vision for the Municipality. | Municipal Manager (LED Unit) | Develop a Tourism strategy by 31st December 2017 | Action plan and letter from COGTA to commence with the development of LED Strategy plan and the Tourism sector plan | 1 | Not On Target | No funding to appoint a service provider. The Cogta District Multi-Disciplinary Team committed during a meeting held on 20 July 2018 to assist the municipality with consolidating the Tourism Sector Plans of the Former dis-established Municipalities. | 1 | n/a | The Cogta District Multi-Disciplinary Team committed during a meeting held on 20 July 2018 to assist the municipality with consolidating the Tourism Sector Plans of the Former dis-established Municipalities. |
| SUSTAINABLE JOB CREATION  BEE & PARTNERSHIPS  SMME, INDUSTRIAL AND SECTOR DEVELOPMENT  SKILLS DEVELOP-MENT  MAINSTREAMING OF 2ND ECONOMY, YOUTH, DISABLED & WOMEN | Develop LED Strategic Plan with an economic Vision for the Municipality. | Municipal Manager (LED Unit) | Develop LED Strategy by 31st December 2017 | Action plan and letter from COGTA to commence with the development of LED Strategy plan and the Tourism sector plan | 1 | Not on Target | No funding to appoint a service provider. The Cogta District Multi-Disciplinary Team committed during a meeting held on 20 July 2018 to assist the municipality with the development of LED strategy. | 1 | n/a | The Cogta District Multi-Disciplinary Team committed during a meeting held on 20 July 2018 to assist the municipality with the development of LED strategy. |
| Creating and enabling environment to attract investment that generates economic growth and job creation | Implement strategic LED Action and Interventions with the aim of creating networks, linkages, referral & support systems, appropriate policies, by-laws, incentives, services and infrastructure that will stimulate and facilitate LED, attract investment, encourage establishment and growth of business and industry in the Dr. Beyers Naude LM. | Municipal Manager (LED Unit) | Implement 2 initiatives identified by the Mohair summit by 30th June 2018. | New KPI | 2 | Not on Target | No output. Council representative to be elected to follow-up those initiatives. | 2 | n/a | Council to Identify representative to sit on the mohair task team. |
| DEVELOPMENT PRIORITY – BACK TO BASICS - GOOD GOVERNANCE |  |  |  |  |  |  | OVERALL PERFORMANCE |  |  |  |
| Objective | Strategy | Depart | KPI | Previous Years Performance 2016/2017 | Annual Target | On Target/Not on Target | Brief Description of Actual Output | Variance | Reasons for Variance | Brief Plan of Action to address KPI Target not achieved. |
| To become the best performing Municipality, in all respects. | Developing a credible Integrated Development Plan that will address the developmental needs of our Community. | Municipal Manager (IDP Unit) | A reviewed and credible IDP for 2018/19. | - Process Plan was developed, adopted and implemented - 14 Ward Councillors were consulted about CBP workshop arrangements. - 14 Ward-based CBP workshops were held. - Full Municipal Situation Analysis was conducted (Institutional and all 14 Wards). - 1 x comprehensive Community Based Planning Report was produced. - 1st & 2nd Draft IDP Project Registers were produced. - 1 x Draft 2017 – 2022 IDP was tabled & adopted. - 4 x IDP Steering Committee meetings were held, incl 1 x Strategic Planning session. - 4 x IDP Representative Forum Meetings were held. - 14 Wards were visited during the Mayoral Outreach. - 21-Day public inspection & comments period was concluded. - Minutes or reports of meetings and consultations were compiled and submitted to the relevant structures for approval or action. - 1 x Final 2017 – 2022 IDP (1st Edition 2017/18) was approved and distributed. Also placed on website with summary. | 1 | On Target | (a) 14 x Mayoral Outreach / PP meetings, (b) 1 x IDP SC meeting, (c) 1 x IDP RF meeting, (d) 1 x first review of 2017 - 2022 IDP approved by Council on 29th May 2018. | none | n/a | n/a |
| To become the best performing Municipality, in all respects. | Having a fully functional Council, with Standing Committees, Fora and other structures. | Corporate Services (Administration Department | Number of Meetings held in terms of year planner by 30 June 2017. (4 Ordinary Council Meetings and 4 Standing Committee meetings) | Ordinary Meeting (18 August 2016, 13 Dec 2016, 6 April 2017 and 13 July 2017 Standing Committees (7 Nov 2016, 6 Dec 2016, 27 Feb 2017, 8, 9 12, 13 & 22 June 2017 | 8 | On Target | This done accordingly. | None | n/a | n/a |
| To become the best performing Municipality, in all respects. | Ensuring that Ward Committees have been established and are functioning properly, and that a CDW has been appointed in each Ward | Municipal Manager | CDW’s deployed at ward level with monthly report submission. | No monthly reports as no CDW’s deployed by COGTA. Meeting Held with COGTA National and provincial to discuss the matter and to speed up the process. Recruitments to commence in new financial year. | 12 | Not on Target | CDW’s are deployed by COGTA. Not all wards have CDW’s. | 12 | Emphasis is placed on vacant CDW post at MUNIMEC and Provincial IGR meeting for posts to be filled. | Emphasis is placed on vacant CDW post at MUNIMEC and Provincial IGR meeting for posts to be filled. |
| To become the best performing Municipality, in all respects. | Having a fully functional Council, with Standing Committees, Fora and other structures. | Corporate Services (Administration | Number of MPAC meetings to assist with oversight function until 30 June 2018. | 3 MPAC meetings held | 4 | On Target | Quarterly MPAC meeting held during the 4th quarter. 27 Nov 2017 15 March 2018 23 March 2018 20 June 2018 | None | n/a | n/a |
| To become the best performing Municipality, in all respects. | Having a fully functional Council, with Standing Committees, Fora and other structures. | Corporate Services (Administration | Number of Audit Committee meetings to assist with oversight function until 30 June 2018. | 30 Aug & 8 Dec 2016, 1 March & 26 June 2017 | 4 | On Target | Audit Committee meeting held during the 4th quarter. | None | n/a | n/a |
| To become the best performing Municipality, in all respects | Installing and maintaining effective and efficient communications and other systems that will improve information-sharing, enhance public participation and promote socio-economic development. | Corporate Services (Human Resource Department | Ensure that the LLF is functioning properly and fulfilling its mandate by having 6 Meetings annually | 6 LLF’s meeting held | 6 | Not On Target | Not on Target | Only 2 LLF’ s commenced during the 17/18 FY | LFF meetings to be held at least once per quarter. | n/a |
| To become the best performing Municipality, in all respects. | Installing and maintaining effective and efficient communications and other systems that will improve information-sharing, enhance public participation and promote socio-economic development. | Municipal Manager (Communication Unit) | Implement Communication Action Plans by providing quarterly progress reports by 30th June 2018. | Communication strategy and action plan has been developed and approved by Council. Newsletter distributed on a quarterly basis internally and externally. Limited implementation | 4 | Not On Target | No output | Communication action plan to be reviewed for 2018/2019 | n/a | n/a |
| To become the best performing Municipality, in all respects | Installing and maintaining effective and efficient communications and other systems that will improve information-sharing, enhance public participation and promote socio-economic development. | Municipal Manager (Communication Unit) | Number of quarterly External Newsletters distributed to stakeholders by 30th June 2018 | New KPI | 60 000 | Not On Target | No newsletter developed during the 4th quarter. | 60 000 | Tools of trade not available for developing quarterly newsletters and delay in appointment of communication official. | Communication official to be appointed and provided with the required tools of trade. |
| To become the best performing Municipality, in all respects. | Installing and maintaining effective and efficient communications and other systems that will improve information-sharing, enhance public participation and promote socio-economic development. | Municipal Manager (Communication Unit) | Number of Interviews Held with the Mayor and submitted to the local Newspaper (The advertiser) by 30th June 2018. | New KPI | 4 | On Target | 4 interviews held throughout the financial year. | none | n/a | n/a |
| To become the best performing Municipality, in all respects. | Installing and maintaining effective and efficient communications and other systems that will improve information-sharing, enhance public participation and promote socio-economic development. | Corporate Services (Administration Department | Maintain updated housing beneficiary list and submit to Department of Human settlement on a quarterly basis by 30th June 2018 | New KPI | 4 | On Target | Quarterly housing needs register will be submitted to corporate service standing committee in August 2018. No report for the 4th quarter was submitted. | None | n/a | n/a |
| To become the best performing Municipality, in all respects. | Ensuring that Ward Committees have been established and are functioning properly, and that a CDW has been appointed in each Ward. | Municipal Manager | Quarterly Ward Committee meetings until 30 June 2018 | No new ward committee elections held. Ward committee’s to be elected in new financial year. | 4 | Not on Target | Quarterly ward committee meetings held in wards, excluding ward 5. | n/a | Ward Cllr disputes legitimacy of Ward Committee Members elected. | Ward Cllr disputes legitimacy of Ward Committee Members elected. |
| To become the best performing Municipality, in all respects | Providing Free Basic Services and Indigent Support. | Budget and Treasury (Finance Department | Extend the Indigent Register by registering 120 Houses by 30th June 2018. | 187 Households registered | 120 | On Target | 243 new applications registered for the year. | +123 | More indigents registered | n/a |
| DEVELOPMENT PRIORITY – BACK TO BASICS - SOUND FINANCIAL MANAGEMENT |  |  |  |  |  |  | OVERALL PERFORMANCE |  |  |  |
| Objective | Strategy | Depart | KPI | Previous Years Performance 2016/2017 | Annual Target | On Target/ Not on Target | Brief Description of Actual Output | Variance | Reasons for Variance | Brief Plan of Action to address KPI Target not achieved. |
| To become a financially viable and sustainable Municipality. | The development and implementation of a Funding Strategy. | Budget and Treasury (Finance Department | 100% expenditure of Municipal FMG and Audit Improvement Grant by 30th June 2018. | New KPI | 100% | On Target | 100% Expenditure | none | n/a | n/a |
| To receive a Clean Audit Opinion from the Auditor-General. | Implementation and execution of an Audit Action Plan. | Municipal Manager | 100% Reporting compliance by submitting s71, s72 and s52d reports within legislated timeframes 30th June 2018. | 100% submission of financial information not achieved due to amalgamation process, system integration, mSCOA compliance and capacity challenges | 100% | On Target | All reporting done as per MFMA. | none | n/a | n/a |
| To receive a Clean Audit Opinion from the Auditor-General. | Implementation and execution of an Audit Action Plan. | Municipal Manager | Improve Outcome of the AG report: Execute action plan to address previous findings by 30 June 2018. | Audit Action Plan has been developed and monitored on a monthly basis with progress reports submitted to council. | 1 | Not on Target | 10 items not started, 32 in process and 27 completed. | none | n/a | Number of items is currently indicated as being in process and will only be concluded in the new Financial year 2018/19 |
| To receive a Clean Audit Opinion from the Auditor-General. | Implementation and execution of an Audit Action Plan. | Budget and Treasury (Supply Chain Department | Verification of the completeness of the Asset Register (Asset Register compliant to GRAP standards) | A full scope asset verification process has been conducted within the municipality and a compilation of a Grap compliant asset register will be submitted with Annual financial statement to the Auditor General on 31 August 2017. | 100% | On Target | All purchases captured, Recon performed and annual reviewed performed | None | n/a | n/a |
| To become a financially viable and sustainable Municipality. | Alignment of the Budget to the IDP’s Development Priorities. | Municipal Manager | Percentage CAPEX of budget spend by 30th June 2018. | 27% Capital expenditure which is funded by Grants not 100% spent due to amalgamation process challenges, however application for rollover of allocated funds has been submitted to National Treasury | 100% | Not On Target | 72% CAPEX budget spent | 28% | RBIG Grant was reduced due to Dept of Water Affairs not having sufficient funding | n/a |
| To become a financially viable and sustainable Municipality. | Alignment of the Budget to the IDP’s Development Priorities. | Municipal Manager | Percentage OPEX of budget spend by 30th June 2018. | 65%. Operational Expenditure budget has not been spent due to cash flow challenges encountered by the municipality as a result of debt owed mainly to Eskom and AG. The poor collection of debt at just over 70% has also contributed to the cash flow challenges with employee cost constantly being a challenge to pay. | 80% | On Target | 95% of OPEX budget spent | none | n/a | n/a |
| To adopt a realistic, credible and funded Annual Budget | Alignment of the Budget to the IDP’s Development Priorities. | Municipal Manager | 2018//2019 Budget approved by Council by 31 May 2018. | The budget has been approved on 23 May 2017 with budget related policies and tariffs. | 1 | On Target | Final budget approved by council on the 29th May 2018 and made public | none | n/a | n/a |
| To become a financially viable and sustainable Municipality. | Implementation and execution of the Financial Recovery Plan – robust plans for the repayment of debt and/or maintain a healthy level of cash reserves and assets in order to meet unexpected costs. | Budget and Treasury (Finance department | Improve collection rate on service debtors to address cash flow constraints by 30th June 2018 (Service debtors/service debt collected) | New KPI | 80% | On Target | Collection rate for the year 90.28% | none | n/a | n/a |
| To become a financially viable and sustainable Municipality. | Implementation and execution of the Financial Recovery Plan – robust plans for the repayment of debt and/or maintain a healthy level of cash reserves and assets in order to meet unexpected costs. | Budget and Treasury (Finance department | Financial recovery plan implemented and monitored by submissions quarterly to EXCO by 30th June 2018. | New KPI | 1 | Not on Target | No quarterly reports submitted. Revised. Recovery plan was approved in December 2017. | 1 | n/a | Reports to be submitted quarterly during 2018/2019 |
| To become a financially viable and sustainable Municipality. | Stringent implementation and execution of the Municipality’s Credit Control & Debt Collection Policy. | Budget and Treasury (Finance department | Effective control over collection of property rates: by 30 June 2018. Property rates collected/ property rate debtors. | New KPI | Ensure average 80% recovery rate of property rates billed by 30 June 2018. | On Target | Percentage is 95.39% for year to date 30 June 2018. | none | n/a | n/a |
| To become the best performing Municipality, in all respects. | Implementation and execution of the Financial Recovery Plan – robust plans for the repayment of debt and/or maintain a healthy level of cash reserves and assets in order to meet unexpected costs | Budget and Treasury (Finance department | Number of interns appointed in Finance Department by 30 June 2018. | New KPI | 7 | On Target | 7 interns appointed | none | n/a | n/a |

2016/2017 PERFORMANCE – TARGET ACHIEVEMENT VS 2017/2018 PERFORMANCE – TARGET ACHIEVEMENT

| 2016/2017 - CAPITAL BUDGET PROJECTS | 2017/2018 – CAPITAL BUDGET PROJECT |
| --- | --- |
| Infrastructure Development Number of projects: 15 Number of projects completed/ on target: 4 Number of projects Not on Target: 11 Percentage on targets: 27% Institutional Development Number of projects: 15 Number of projects completed/ on target: 6 Number of projects Not on Target: 9 Percentage on targets: 40% Community Development Number of projects: 3 Number of projects completed/ on target: 0 Number of projects Not on Target: 3 Percentage on target: 0% Total Number of Capital Budget Projects per KPA = 34 Number of Key Performance Indicators on Target/Completed = 10 Number of Key Performance Indicators Not on Target = 22 Percentage on Target = 30% | Infrastructure Development Number of projects: 10 Number of projects completed/ on target: 10 Number of projects Not on Target: 0 Percentage on targets: 100% Institutional Development Number of projects: 21 Number of projects completed/ on target: 8 Number of projects Not on Target: 13 Percentage on targets: 38% Community Development Number of projects: 1 Number of projects completed/ on target: 0 Number of projects Not on Target: 1 Percentage on target: 0% Total Number of Capital Budget Projects per KPA = 32 Number of Key Performance Indicators on Target/Completed = 19 Number of Key Performance Indicators Not on Target = 13 Percentage on Target = 59% |

| 2016/2017 - OPERATIONAL KPI’S / PROJECTS | 2017/2018 – OPERATIONAL KPI’S / PROJECTS |
| --- | --- |
| Development Priority: Infrastructure Development Number of Indicators: 2 Number of indicators on target: 2 Number of indicators not on target: 0 Percentage on target: 100% Development Priority: Local Economic Development Number of Indicators: 5 Number of indicators on target: 2 Number of indicators not on target: 3 Percentage on target: 40% Development Priority: Institutional Development Number of Indicators: 15 Number of indicators on target: 10 Number of indicators not on target: 5 Percentage on target: 67% Development Priority: Community Development Number of Indicators: 5 Number of indicators on target: 3 Number of indicators not on target: 2 Percentage on target: 60% Development Priority: Service Delivery Excellence Number of Indicators: 17 Number of indicators on target: 9 Number of indicators not on target: 8 Percentage on target: 53% Development Priority: Sound Financial Management Number of Indicators: 16 Number of indicators on target: 7 Number of indicators not on target: 9 Percentage on target: 44% Total Number of Key Performance Indicators per KPA = 60 Number of Key Performance Indicators on Target/Completed = 33 Number of Key Performance Indicators Not on Target = 27 Percentage on Target = 55% OVERALL ORGANISATIONAL PERFORMANCE BASED ON SDBIP : 46% | Development Priority: Infrastructure Development Number of Indicators: 7 Number of indicators on target: 4 Number of indicators not on target: 3 Percentage on target: 57% Development Priority: Local Economic Development Number of Indicators: 9 Number of indicators on target: 1 Number of indicators not on target: 8 Percentage on target: 11% Development Priority: Institutional Development Number of Indicators: 14 Number of indicators on target: 11 Number of indicators not on target:3 Percentage on target: 79% Development Priority: Community Development Number of Indicators: 5 Number of indicators on target: 3 Number of indicators not on target: 2 Percentage on target: 60% Development Priority: Back to Basics - Good Governance Number of Indicators: 12 Number of indicators on target: 7 Number of indicators not on target: 5 Percentage on target: 58% Development Priority: Back to Basics - Sound Financial Management Number of Indicators: 11 Number of indicators on target: 8 Number of indicators not on target: 3 Percentage on target: 73% Total Number of Key Performance Indicators per KPA = 58 Number of Key Performance Indicators on Target/Completed = 34 Number of Key Performance Indicators Not on Target = 24 Percentage on Target = 59% OVERALL ORGANISATIONAL PERFORMANCE BASED ON SDBIP: 59% |

CONCLUSION

The Dr. Beyers Naudé Local Municipality served the community greatly during the 2017/2018 financial year.  This overview clearly demonstrates the commitment of the municipality to ensure that the local community has access to basic services.  59 % of projects / Key performance indicators are on Target, however the percentage can be more, if effective project planning takes place in the beginning of the financial year. It is crucial that the SDBIP, Performance management plans and Procurement plan are adhered to by departmental heads in order for the Municipality to be on Par with what is set out in the IDP.

More attention will be placed on the performance of Local Economic development of the municipality, and many more KPI’s will be added to this KPA in the 2018/2019 financial year. The municipality needs to create an enabling environment for Economic growth, Investment attraction, Enterprise development and retention.

Due to various challenges, 41% of the planned targets could not be met. As a Municipality, we will respond to these outstanding targets and will duly report on the progress made to address those targets. This progress report will be submitted to Council during January 2019 together with the Mid-year Budget and Performance Assessment Report 2018/2019.