TABLE OF CONTENTS

- Introduction

- Income Budget

- Expenditure Budget

- Capital Budget by Source

- Capital Expenditure by Project and Ward

- Service Delivery Targets and Performance Indicators

Honourable Mayor’s Foreword

The Municipal Systems Act, 32 of 2000 requires all municipalities to develop 5 year Integrated Development plans and review them annually. The Dr. Beyer’s Naude Local Municipality has developed the IDP within an approved IDP process plan and engaged in a consultation process to ensure that communities become part of the planning and decision making processes. The process was followed by the development of projects emanating from the needs and challenges identified in the strategic planning session and IDP public participation.

Chapter 6 of the MSA 32 of 2000 requires that all municipalities must develop a performance Management System that will monitor the implementation of the IDP. The SDBIP of the Municipality serves as a performance contract between the Administration, the Council and the Community expressing the goals and Objectives of the Council.

The Honourable Mayor D. de Vos

The SDBIP displays Projects and programmes that are to be implemented as Key Performance Indicators, these Key performance Indicators are linked to development priorities within the IDP. The SDBIP only covers those projects and programmes that have budget and human resource capital support. Performance targets were set within the SDBIP and will be monitored on continuous bases and assessed on quarterly bases.

Despite the challenges faced in the transition from the former municipalities to the Dr. Beyer’s Naude Local Municipality, It is with great pride I can highlight the effort taken by the municipality to ensure that the IDP and Budget processes are aligned; that the SDBIP is linked to the IDP and that public participation has been done as required by legislation.  It’s a pleasure to present to you the 2017/2018 SDBIP as a performance agreement between Council and the Community to improve the lives of our people.

In closing, I would like to thank Council Members for their commitment in realizing the goals of improving the lives of our people. I would further thank the administration who, in spite of all challenges, continue to pay attention to the task at hand. Yes, we do have challenges, but these are not what we focus on, but what we built energy on and recommit to working extra hard in achieving our goal: to make Dr. Beyers Naude Local Municipality the best in the Country.

- INTRODUCTION

OBJECTIVE

The primary objective is to develop a 12 month plan within which the Municipality has to achieve the following:

- The services represented by the expenditure in the budget

- The income to fund the service delivery.

Circular 13 from National Treasury attempts to commit all stakeholders to the agreement to work towards specific objectives.  This is done within the framework of consultation as outlined in Chapter 4 of the Systems Act.

The secondary objective is to reduce to writing the activities of the organization so that it may be subjected to assessment and benchmarking.

It serves as a supplementary support document to the approved budget represented as a policy document. It further serves as a record of the Key Performance Areas (KPA) with their corresponding Key Performance Indicators (KPI) or Critical Success Factors (CSF).

DEFINITION

THOSE TANGIBLE AND INTANGLE GOOD(S) AND/OR SERVICE(S) THAT ARE A PRODUCT OF OUR EXISTENCE BY MANDATE

S   ------   SERVICE    ---------

THE “VEHICLE” USED TO ACHIEVE THE SERVICE AT THE RIGHT TIME, PLACE , QUANTITY AND QUALITY

D   ------   DELIVERY   --------

A POLICY DOCUMENT, THAT RECORDS REALISTIC INCOME AND EXPENDITURE AS WELL AS THE INTENDED ACTIVITIES

B   ------   BUDGET   ----------

I ------ IMPLEMENTATION -- THIS REFERS TO THE CONSEQUENCE AND REALIZATION OF DELIVERY. THE ACTION OR EFFORT

THIS IS THE SDBIP STRATEGY DOCUMENT SO AGREED BY THE STAKEHOLDERS.

P   ------   PLAN   ---------------

Once the budget has been approved, the SD&BIP must be presented to the Mayor by the Accounting Officer, after consultations with Senior Managers and other Head of Departments, at least one week before the commencement of the new financial year.

Even though it is not a policy document like the IDP and the Budget, it is a vital tool for planning and strategy development.  The monitoring capability of the PMS system is vitally important towards reporting and achieving service delivery.  It is a vital tool for decision-making and contracting mandates from communities.

The layers of this document will see the objectives reported by the following listed components as well as by comparisons to the Organizational Performance and, in turn, linked to the individual directors and their activities within their votes.

The major components of the SDBIP are:

1.	Projections of budgeted income and actual income per vote and per activity

2.	Projections of budgeted expenditure against actual per vote and per activity

3.	Projections of the service (KPA) achieved against budget spending and comment.

These will be illustrated in both tabular and graphic format in the (Final approved SDBIP)

The procedure

The SDBIP is fundamentally divided into two sections namely:

The Service Delivery Component (SD)

This is derived from the Performance Management System from which the KPA and its score are extracted.  Here we analyse the purpose for the existence of the budget into the KPA and the corresponding KPI together with its delivery mechanism.

The Budget Implementation Plan (BIP)

Hereto we made use of controlled stationers to provide the detail associated with every line on the budget.  This was to determine the justification for the budget as well as ascertain its directive in support of a KPA.

The following Departments exist:

Main Vote/Department

EXECUTIVE & COUNCIL

CORPORATE SERVICES - ADMINISTRATION

CORPORATE SERVICES - COMMUNITY SERVICES

CORPORATE SERVICES - PROTECTION

FINANCIAL SERVICES

TECHNICAL SERVICES - ENGINEERING

TECHNICAL SERVICES - ELECTRICAL

The Concept

The concept is based on the idea that spending will be indicative of service delivery as a major consideration of whether the KPA was achieved. It is supplemented by an overview report by the Director and endorsed by the Municipal Manager.

LEGISLATION

The following legislation applies:

The Municipal Finance Management Act 2004, Chapter 7, Section 53 (c)(ii), which states:

“Take reasonable steps to ensure the Municipality’s SD&BIP is approved by the Mayor within 28 Days after the approval of the budget and made public no later than 14 days after that”

Circular 13, from National Treasury provides the departure point for the SDBIP.

Chapter 8 of the MFMA stipulates that the Accounting Officer must submit a draft of the SDBIP to the Mayor within 14 days of the budget being approved as well as a draft of the annual performance agreements required by the Municipal Systems Act.

Section 72 (1), (a), (ii) states “the accounting officer of the municipality must by 25 January of each year assess the performance of the municipality during the first half of the financial year, taking into account the municipality’s service delivery performance during the first half of the financial year, and the service delivery targets and performance indicators set in the service delivery and budget implementation plan”

These sections leads us to the budget monitoring requirements of section 71 and the rest of section 72 of the MFMA where it is stipulated that the Mayor must check whether  the budget is being implemented in accordance with the SDBIP.

It should be noted that service delivery and its related expenditure is based on the ability to fund the budget.  Should a shortage of income be realized, an Adjustment Budget, in terms of the MFMA, will be tabled.

The effect is that expenditure will be reduced in line with realistic income.  This in turn means that service as contained in the SDBIP will then be reduced as well.

ROLEPLAYERS

The roleplayers and their respective roles include:

    - The Mayor

As head of the Plenary Council and to provide political leadership and direction. Section 21(a), (b)

    - The Ward Councillor/PR Councillor

As promoter of the Ward Committee structure or as representative of a certain sector of the population.

    - The Municipal Manager

As Accounting Officer and administratively charged

    - The Chief Financial Officer

As advisor to the AO and responsible for the administration of the budget. (Section 84, (1).

Senior accountants for reporting and assistance. Delegation: MFMA

    - Senior Managers

As appointed as head of departments for the respective services, Section 78, (1).

    - Senior officials and Section Heads

Reporting to Senior Managers and acting under delegation from their supervisors.

    - Unions

As the recognized body for organized labour being SAMWU and IMATU.

    - External Parties

- National Treasury: MFMA

- Provincial Officers and Departments: MFMA

    - Internal Documents

- Integrated Development Plan

- Spatial Development Plans

- Local Economic Development Plan

    - Other

ORGANOGRAM AND INSTITUTIONAL ARRANGEMENTS

The organogram depicts the structure of employees that support and deliver the objectives of the organization.  The budget is divided into activities together with the employees associated with it.

Income Budget by Source

EXPENDITURE BUDGET BY PROJECT AND WARD

| IDP No. | Objective | Strategy | Baseline Indicator | Project Name | KPI | Wards | Responsible Department | 2017/2018 Funding Source/ Budget | Annual Target | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INFRASTRUCTURE DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 111 | To adequately increase bulk water storage, upgrade reticulation systems, secure permanent water supply and properly maintain all infrastructure | Upgrade reticulation system by systematically replacing old installations. | Existing infrastructure not efficient for demand. | Refurbishment of Borehole Equipment and Installation of Bio- Tower Water Treatment | Supply and installation of 1 borehole pump, installation of 1 water meter, installation of 1 package water treatment plant. Installation of 1 MCC panel for the package plant in Jansenville by 30th June 2018. | 10,11 | Technical Department | External MIG 2,131,800 | 4 | Appointment of Consultant | Appointment of contractor | Construction of 1 borehole and installation of 1 water meter. | Installation of package water treatment plant and Certificate of Completion |
| 112 | To adequately increase bulk water storage, upgrade reticulation systems, secure permanent water supply and properly maintain all infrastructure | Upgrade reticulation system by systematically replacing old installations. | The Demand exceeds supply | Willowmore Bulk Water Supply - Wilgerkloof | Construction of uPVC 2100m pipeline in Willowmore by 31 March 2018. | 8,9,13 | Technical Department | External MIG 3,015,610 | 2100m pipeline | Planning and development of construction plan. | Construction 500m. | Construction of 1600m pipeline and Certificate of completion. | n/a |
| 112 | To adequately increase bulk water storage, upgrade reticulation systems, secure permanent water supply and properly maintain all infrastructure | Upgrade reticulation system by systematically replacing old installations. | The Demand exceeds supply | Willomore Bulk Water Supply – Upgrading, extensions and additional | Construction of uPVC 2000m pipeline in Willomore by 30th June 2018. | 8,9,13 | Technical Department | External MIG 3,610,461 | 2000m pipeline | n/a | n/a | Procurement process | Construction of 2000m pipeline and Certificate of completion. |
| 114 | To adequately increase bulk water storage, upgrade reticulation systems, secure permanent water supply and properly maintain all infrastructure | Upgrade reticulation system by systematically replacing old installations. | 7 existing boreholes in Aberdeen, however the demand exceeds supply. | Aberdeen: Upgrading of Bulk Water: Supply Phase 2 | Drilling and equipping of 2 boreholes and 1 Hydrological report in Aberdeen by 30th June 2018. | 8,9,13 | Technical Department | External MIG 1,109,073 | 2 boreholes and 1 Hydrological Report | n/a | Appointment of Contractor | Drilling of Borehole and Hydrological report. | Certificate of Completion n/a |
| 118 | To adequately increase bulk water storage, upgrade reticulation systems, secure permanent water supply and properly maintain all infrastructure | Upgrade reticulation system by systematically replacing old installations. | Existing Dam supply not sufficient for drought periods. | Graaff-Reinet Emergency Water Supply Scheme | Construction of 1 steel reservoir and installation of 315mm bulk rising main in Graaff-Reinet by 30th June 2018. | 2,3,4,5,6,7,14 | Technical Department | External RBIG 22,000,000 | 1 Steel Reservoir, 315mm rising main | Construction of reservoir and rising main. | Certificate of Completion | n/a | n/a |
| 131 | Solid Waste Disposal Sites (Landfills), that are compliant, have adequate capacity and are properly managed and maintained | Systematically upgrade existing infrastructure; replace and rehabilitate where applicable. | Existing site has reached capacity. | Graaff-Reinet: Upgrading Solid Waste Site of 2 New Cells | Number of cells constructed in Graaff-Reinet Solid Waste Disposal Facility by 30th June 2018. | 2,3,4,5,6,7,14 | Technical Department | External MIG 675,047 | 2 cells | n/a | Clearing the existing site. | Construction of 1 cell | Construction of 1 cell and Certificate of Completion |
| 141 | To adequately upgrade the electrical supply and install the necessary electrical infrastructure, as well as regular maintenance thereof | Conduct an audit of electrification needs and infrastructure in the Dr Beyers Naudé LM. | 64 RDP houses constructed in Willomore | Upgrade Infrastructure | Installation of 1.8KM overhead powerlines in Graaff-Reinet AND Electrification of 64 RDP Houses in Willowmore by 30th June 2018. | 8,9,12,13 | Electrical Department | External DOE 7,000,000 | 1.8km powerline AND 64 RDP houses electrified | Tender process and appointment of Consultant | Appointment of Contractor | Electrification of 64 RDP Houses | Construction 1.8km Overhead Powerlines and Certificate of completion |
| 147 | To adequately upgrade the electrical supply and install the necessary electrical infrastructure, as well as regular maintenance thereof | Conduct an audit of electrification needs and infrastructure in the Dr Beyers Naudé LM. | No standby/ Emergency transformers within the Dr. Beyers Naude Local Municipality. | Transformers | Number of Standby Transformers Purchased by 30th June 2018. | 1-14 | Electrical Department | Internal 336,120 | 1 | n/a | n/a | Tender process | Delivery of 1 Transformer |
| 163 | To adequately construct, upgrade or install Streets & Stormwater networks and to maintain them on a regular basis | Systematically upgrade existing infrastructure; replace and rehabilitate where applicable | Gravel roads currently in Jansenville and Klipplaat. | Jansenville /Klipplaat roads and storm water drainage Rehabilitation | Paving of 1500m2 roads in Jansenville and 1500m2 roads in Klipplaat by 30th June 2018. | 10,11 | Technical Department | External MIG 2,724,871 | 3000m2 of road paved | Construction Of 1000m2 | Construction Of 1000m2 | Construction Of 1000m2 | Certificate of Completion |
| 163 | To adequately construct, upgrade or install Streets & Stormwater networks and to maintain them on a regular basis | Systematically upgrade existing infrastructure; replace and rehabilitate where applicable | Existing cut-off drain in Umasizakhe and Kroonvale needs to be rehabilitated. | Graaff Reinet roads and storm water drainage Rehabilitation | Construction of a 4500m3 berm and progress report by 30th June 2018. | 5,6 | Technical Department | External MIG 5,555,489 | 4500m3 berm and progress report. | Tender Processes and appointment of consultant | Design report | Appointment of Contractor | Construction of a 4500m3 berm cut - off drain and Progress report |
| COMMUNITY DEVLOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 201 | Solid Waste Disposal Sites (Landfills), that are compliant, have adequate capacity and are properly managed and maintained | Systematically upgrade existing infrastructure; replace and rehabilitate where applicable. | Existing soccer field with pavilion requires upgrading | Graaff-Reinet: Development of a Soccerfield in Kroonvale, phase 2 | Construction of one 130m2 ablution facility at the Kroonvale soccerfield by 30th June 2018 | 5 | Technical Department | External MIG 1,034,649 | 130m2 ablution facility. And progress report. | n/a | n/a | Appointment of consultant. | Construction of ablution facility with progress report. |
| INSTITUTIONAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 317 | To improve service delivery by replacing the current fleet with more reliable vehicles. | Purchase vehicles or plant required for delivering the necessary services. | Fleet not sufficient for vast municipal area | VEHICLES | Number of Refuse trucks purchased by 30th June 2018 | Institutional | Community Services | External SBDM 1,000,000 | 2 refuse trucks | n/a | n/a | Sign SLA and Resolution. Start with procurement of 2 refuse trucks. | Delivery of refuse trucks |
| 330 | To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant | Equip offices and areas of service delivery with adequate resources. | 8 air conditioners currently. 2 air conditioners needed for additional office space. | Air Conditioners | Number of Air conditioners purchased by 30 September 2017. | Institutional | Supply Chain/Assets Department | External FMG 20,000 | 2 | Quotations sourced. Purchased, delivery and Installation of Air conditioner. | n/a | n/a | n/a |
| 330 | To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant | Equip offices and areas of service delivery with adequate resources. | Additional furniture required | Air Conditioners | Number of Air conditioners purchased by 30 September 2017. | Institutional | Institutional | Internal 60,000 | 6 | n/a | n/a | Procurement and delivery of 3 air conditioners | Procurement and delivery of 3 air conditioners |
| 330 | To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant | Equip offices and areas of service delivery with adequate resources. | Additional furniture required once office space has been secured. | Air Conditioners | Number of air conditioners purchased by 30th June 2018. | Institutional | Internal Audit | External FMG 15,000 | 1 | n/a | n/a | n/a | Procurement and installation of 1 air conditioner |
| 335 | To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant | Equip offices and areas of service delivery with adequate resources. | Additional furniture required | Air Conditioners | Number of air conditioners purchased by 30th June 2018. | Institutional | Corporate services/ Customer Care | External MDTG NT 15,000 | 1 | n/a | n/a | n/a | Procurement and delivery of 1 air conditioner |
| 331 | To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant | Equip offices and areas of service delivery with adequate resources. | Additional furniture required once office space has been secured. | Office Furniture | Purchase 4 Cabinets, 3 Shelves, 14 Tables, and 21 Chairs by 31 December 2017. | Institutional | Finance Department | External FMG 150,000 | 42 | Source Quotations | Purchase and Delivery of Office Furniture | n/a | n/a |
| 331 | To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant | Equip offices and areas of service delivery with adequate resources. | Additional furniture required once office space has been secured. | Office Furniture | Purchase 2 desks by 30th June 2018 | Institutional | Internal Audit | External FMG 22,000 | 2 | n/a | n/a | n/a | Procurement and delivery of 2 desks. |
| 334 | To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant | Equip offices and areas of service delivery with adequate resources. | Cleaning appliances purchased annually. | Cleaning Appliances | Number of Polishers and Vacuum cleaners to be purchased by 30th September 2017. | Institutional | Finance Department | External FMG 30,000 | 2 | Source quotations. Purchase and delivery of cleaning appliances. | n/a | n/a | n/a |
| 341 | To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant | Equip offices and areas of service delivery with adequate resources. | Fire equipment purchased annually | Tools and Equipment | Number of Specialised Occupational Health and Safety (Fire) equipment purchased by 31 December 2017. | Institutional | Protection Service Department | Internal/ External 50,000 | 14 | Source Quotations | Purchased and Delivery of Equipment | n/a | n/a |
| 342 | To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant | Equip offices and areas of service delivery with adequate resources. | 5 Hand Held devices in Graaff-Reinet. | Tools and Equipment | Number of Hand – Held devices purchased for meter reading throughout the Dr. Beyer’s Naude Local Municipality 31 December 2017. | Institutional | Finance Department | External FMG 70,000 | 4 | n/a | Request quotation from Service provider. Purchased and delivery of Equipment. | n/a | n/a |
| 345 | To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant. | Equip offices and areas of service delivery with adequate resources. | Equip office necessary equipment | Machinery Office, e.g. shredders | Purchase a shredder and overhead projector by 30th June 2018. | Institutional | Internal Audit | External FMG 9000 | 2 | n/a | n/a | n/a | Procurement and delivery of shredder and overhead projector. |
| 351 | To improve overall efficiency of ICT ~ administration, billing, record keeping, information sharing and communication; to ensure optimal, cost-effective production and quality service delivery | Conduct a comprehensive ICT audit. | 160 Exchange hosted mailboxes | IT Software | Number of Exchange Hosted mailboxes purchased By 31 September 2017. | Institutional | Corporate Services | External FMG 70,000 | 10 | 10 Exchanged Hosted Mailboxes purchased. | n/a | n/a | n/a |
| 351 | To improve overall efficiency of ICT ~ administration, billing, record keeping, information sharing and communication; to ensure optimal, cost-effective production and quality service delivery | Conduct a comprehensive ICT audit. | 13 Windows pro Licenses | IT Software | Number of Windows pro licenses purchased by 31 September 2017. | Institutional | Corporate Services | External FMG 40,000 | 10 | 10 Windows pro licenses purchased. | n/a | n/a | n/a |
| 351 | To improve overall efficiency of ICT ~ administration, billing, record keeping, information sharing and communication; to ensure optimal, cost-effective production and quality service delivery | Conduct a comprehensive ICT audit. | 15 Microsoft Office H&B Licenses | IT Software | Number of Microsoft Office H&B Licences purchased by 31 September 2017. | Institutional | Corporate Services | External FMG 50,000 | 10 | 10 Microsoft Office H&B Licences purchased. | n/a | n/a | n/a |
| 351 | To improve overall efficiency of ICT ~ administration, billing, record keeping, information sharing and communication; to ensure optimal, cost-effective production and quality service delivery | Identify and Implement suitable projects | No Internal Audit software | IT Software | Installation of Internal audit software by 30th June 2018 | Institutional | Internal Audit | External FMG 200,000 | Software installed. | n/a | n/a | .n/a | Tender advertised and Installation of software. |
| 352 | To improve overall efficiency of ICT ~ administration, billing, record keeping, information sharing and communication; to ensure optimal, cost-effective production and quality service delivery | Conduct a comprehensive ICT audit. | 1 Drill, Glue gun, Grinder, Blower, 3 Batteries | IT Hardware | Purchased 1 drill, 2 step ladder, 1 glue gun, 1 crimping tool, 1 network tester) by 31 December 2017. | Institutional | Corporate Services | External FMG 10,000 | 6 | Source quotations | Purchase and Delivery of IT Hardware. | n/a | n/a |
| 352 | To improve overall efficiency of ICT ~ administration, billing, record keeping, information sharing and communication; to ensure optimal, cost-effective production and quality service delivery | Conduct a comprehensive ICT audit. | 40 PC/Laptops | IT Hardware | Number of PC/Laptops purchased by the 31st December 2017. | Institutional | Corporate Services | External FMG 250,000 | 10 | Source quotations | Purchase and delivery of 10 PC/Laptops | n/a | n/a |
| 352 | To improve overall efficiency of ICT ~ administration, billing, record keeping, information sharing and communication; to ensure optimal, cost-effective production and quality service delivery. | Conduct a comprehensive ICT audit. | New KPI | IT Hardware | Number of Computers purchased by the 30th June 2018. | Institutional | Corporate Services/ Customer Care | External MDTG NT 44,000 | 3 | n/a | n/a | Procuremeent process | Delivery of computers |
| 353 | To improve overall efficiency of ICT ~ administration, billing, record keeping, information sharing and communication; to ensure optimal, cost-effective production and quality service delivery | Identify areas in need of systems upgrade and formulate appropriate ICT Plan & Policies (including IT Disaster Recovery). | Jansenville Network upgraded 2016/2017 | IT Infrastructure | Number of Municipal Buildings identified for the Installation of WIFI by 30th June 2018. | Institutional | Corporate Services | External FMG 200,000 | 4 | n/a | n/a | Install WIFI in Engineering building, and Robert Sobukwe Hall. | Install WIFI Town Hall and Willomore Main Office. |
| 354 | To improve overall efficiency of ICT ~ administration, billing, record keeping, information sharing and communication; to ensure optimal, cost-effective production and quality service delivery | Conduct a comprehensive ICT audit. | 12 vending machines within the Dr. Beyer’s Naude Local Municipality | Electronic Systems | Number of Vending Machines purchased by 31 December 2017. | Institutional | Finance Department | External FMG 220,000 | 4 | Ward councillors to identify suitable areas | Source quotations | Supply and delivery | n/a |
| 354 | To improve overall efficiency of ICT ~ administration, billing, record keeping, information sharing and communication; to ensure optimal, cost-effective production and quality service delivery | Conduct a comprehensive ICT audit. | No loudhailers in communication unit | Electronic Systems | Number of Loudhailers purchased by 30th June 2018. | Institutional | Communications Unit | External MDTG EC 9,600 | 8 | n/a | n/a | Procurement of loudhailers | Delivery of Loudhailers |

- SERVICE DELIVERY TARGETS AND PERFORMANCE INDICATORS

| INFRASTRUCTURE DEVELOPMENT– KPA - Infrastructure and Service Delivery |  |  |  |  |  |  | PERFORMANCE MILESTONES |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective | Strategy | Baseline | Budget | Depart | KPI | Annual Target | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| To adequately increase bulk water storage, upgrade reticulation systems, secure permanent water supply and properly maintain all infrastructure. | Identify and implement suitable Projects. | Reservoirs are cleaned annually. | 80,000 | Engineering and Planning | Number of reservoirs cleaned in Graaff-Reinet by 30th June 2018. | 6 | 0 | 0 | 0 | 6 . |
| For all households to have uninterrupted access to good quality, potable water. | Implement Action Plans contained in WSDP and ensure that proper controls and monitoring measures are in place | 156 samples annually | 285,783.00 | Engineering and Planning | Monitor water quality through taking 13 Samples per month. | 156 | 39 Samples | 39 Samples | 39 Samples | 39 Samples |
| For all households to have uninterrupted access to good quality, potable water. | Implement Action Plans contained in WSDP and ensure that proper controls and monitoring measures are in place | 39 samples taken quarterly. 80% of 39 samples should be compliant with drinking water quality standards | n/a | Engineering and Planning | Percentage compliance with drinking water quality standards (micro-bacterialogical) quarterly. | 80% | 80% | 80% | 80% | 80% |
| To adequately upgrade the electrical supply and install the necessary electrical infrastructure, as well as regular maintenance thereof. | Identify and implement suitable Electrification Projects | 1 Oil test sample taken annually and submitted to a laboratory to ensure that the oil meets specifications. | 60,000.00 | Electrical Department | Number of oil test sample reports for a Transformer by 30 June. 2018. | 1 | 0 | 0 | 0 | 1 |
| Effective recycling programmes that will reduce waste volumes at landfill site and create economic opportunities for the Community | Step up educational campaigns to encourage all citizens to take pride in their areas and keep them clean; to recycle at source | No waste management campaigns held in 2016/2017 | 25, 000.00 | Community Services | Number of Waste management Campaigns held at ward meetings, schools and other institutions by 30th June 2018. | 12 | 3 waste management campaigns per quarter | 3 waste management campaigns per quarter | 3 waste management campaigns per quarter | 3 waste management campaigns per quarter |
| The eradication of illegal dumping and littering and creation of clean and healthy urban areas and surrounding environment | Provide adequate waste disposal facilities and containers, as well as regular waste removal service | Regular cleaning throughout the year. | 75,000.00 | Community Services | Number of quarterly reports on Cleaning of illegal dumping sites and waste skips by 30th June 2018. | 4 | Quarterly report on cleaning of all wards | Quarterly report on cleaning of all wards | Quarterly report on cleaning of all wards | Quarterly report on cleaning of all wards |
| The eradication of illegal dumping and littering and creation of clean and healthy urban areas and surrounding environment | Provide adequate waste disposal facilities and containers, as well as regular waste removal service | Regular cleaning of parks and recreational areas | 75, 000.00 | Community Services | Number of reports on cleaning parks and all recreational areas by 30th June 2018. | 4 | Quarterly report on cleaning of all wards | Quarterly report on cleaning of all wards | Quarterly report on cleaning of all wards | Quarterly report on cleaning of all wards |
| COMMUNITY DEVELOPMENT –KPA – Good Governance |  |  |  |  |  |  | PERFORMANCE MILESTONES |  |  |  |
| Objective | Strategy | Baseline | Budget | Depart | KPI | Annual Target | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| To significantly reduce and mitigate the negative impact of disasters and to upgrade road traffic and pedestrian safety, with regular maintenance on installations and infrastructure as an ongoing concern. | Regularly review and update the Municipality’s Disaster Management Plan and ensure that it incorporates threats identified throughout the region | Former municipalities had a disaster management plan. | n/a | Protection Services Department | Review 1 Disaster management plan and approve by council by 30th June 2018 | 1 | Review current Disaster Management Plan, refer to management meeting for input into any amendments | Draft Disaster Management Plan submit to all stakeholders for input | Collate the comments and inputs received | Present Reviewed Disaster Management Plan to Council for approval |
| To fully involve, capacitate and empower the SPU Sector, with special focus on the Disabled, Youth and Women. | Design programmes and arrange events that will encourage the participation of the SPU sector, especially the Disabled, Youth and Women. | 9 August 2016 – Women’s Day 24 September 2016 – Heritage Day 16 December –Reconciliation day Day 21 March 2017 – Human Rights Day 27 April 2017 – Freedom Day 16 June 2017 – Youth Day | 150,000.00 | Municipal Manager/ SPU unit | Monitor 9 Sports & Cultural events Organized for the Community through reports submitted by SPU Officer to the Office of the Municipal Manager by 30th June 2018 | 9 | Women’s Day and Heritage Day commemorations | National Day for disabled persons, World Aids Day, Reconciliation Day and Opening of the festive season | Human Rights Day and Freedom Day commemorations | Youth Day commemoration |
| To fully involve, capacitate and empower the SPU Sector, with special focus on the Disabled, Youth and Women. | Design programmes and arrange events that will encourage the participation of the SPU sector, especially the Disabled, Youth and Women. | Sports council, women’s caucus, Aids Council, Initiation forum | 50,000.00 | Municipal Manager/SPU Unit | Number of SPU Consultative Forums established, namely: Youth Council, Local Sports Council, Local Aids Council, Women’s Forum and Disabled Forum by 31 December 2017. | 4 | MRM Forum, Youth Forum | Disabled Forum | n/a | n/a |
| To fully involve, capacitate and empower the SPU Sector, with special focus on the Disabled, Youth | Design programmes and arrange events that will encourage the participation of the SPU sector, especially the Disabled, Youth and Women. | 4 quarterly reports submitted to the Municipal Manager for 2016/2017 | n/a | Municipal Manager/SPU Unit | Monitor effectiveness of SPU consultative councils/ Forums by providing quarterly reports to the office of the Municipal Manager. | 4 | Quarterly report on all councils/ forums | Quarterly report on all councils/ forums | Quarterly report on all councils/ forums | Quarterly report on all councils/ forums |
| To fully involve, capacitate and empower the SPU Sector, with special focus on the Disabled, Youth | Design programmes and arrange events that will encourage the participation of the SPU sector, especially the Disabled, Youth and Women. | Training centres in Graaff-Reinet, Aberdeen, Nieu-Bethesda, Willomore, Steytlerville, Baviaans Kloof, Rietbron. Recreation Centre in Graaff-Reinet | 100,000.00 | Municipal Manager/SPU Unit | Number of training programmes for vulnerable groups especially youth and disabled citizens by 30th June 2018. | 8 | Job Readiness training in Graaff-Reinet and Jansenville. AET Training in Graaff – Reinet and Jansenville ABET Training from 24 July 2017. Computer training in Willomore/ Steytlervile/ Rietbron through the year | Skills development training Steytlerville and Willomore. Job readiness training throughout BNLM Computer training in Willomore/ Steytlervile/ Rietbron through the year | Co-operative Governance training throughout BNLM Entrepreneurship development programme throughout BNLM Computer training in Willomore/ Steytlervile/ Rietbron through the year | Arts and Crafts Training throughout BNLM Computer training in Willomore/ Steytlervile/ Rietbron through the year |

| INSTITUTIONAL DEVELOPMENT - KPA – Organisational Transformation & Institutional Development |  |  |  |  |  |  | PERFORMANCE MILESTONES |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective | Strategy | Baseline | Budget | Depart | KPI | Annual Target | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| To recruit staff with adequate qualifications, skills, training and experience. | Finalise the review of the Staff Establishment as a matter of urgency | Staff establishment not completed in 2016/2017 financial year. | 200, 000.00 | Human Resource Department | Develop an organizational structure by 31 December 2017. | 1 | Consultant to workshop proposed Organogram with Council and table before Council for adoption. | n/a | n/a | n/a |
| To recruit staff with adequate qualifications, skills, training and experience. | Finalise the review of the Staff Establishment as a matter of urgency | No staff placed within the Dr. Beyer’s Naude Local Municipality | n/a | Human Resource Department | 100% Implementation of placement policy through placement of staff based on approved Staff establishment by 31 March 2018 | 100% | Establishment of a placement committee. | Finalize job descriptions for each proposed post in staff establishment, and commence with placement of staff. | Placement of staff. | n/a |
| To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant. | Implement Plan & Policies and upgrade systems accordingly; provide suitable training to enable staff to utilize these systems optimally and correctly. | No delegation register adopted by Council. | n/a | Human Resource Department | Number of Delegation registers developed by 31 December 2017. | 1 | Develop delegation register. | Workshop plan with all stakeholders. Adoption and approval by Council. | n/a | n/a |
| To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as legally compliant | Implement Plan & Policies and upgrade systems accordingly; provide suitable training to enable staff to utilize these systems optimally and correctly. | No equity plan adopted by Council | n/a | Human Resource Department | Number of employment equity plans developed by 31 December 2017. | 1 | Develop an employment equity plan | Workshop with Council and stakeholders. Table before Council for adoption. | n/a | n/a |
| To improve service delivery by replacing the current fleet with more reliable vehicles. | Make adequate provision on the annual Budget to address these areas as an ongoing concern. | No action plan | n/a | Corporate services | Develop an action plan for the maintenance and service of all municipal vehicles by 30 June 2018. | 1 | Develop Action Plan | Workshop Action Plan | Execute Action Plan | Execute Action Plan |
| To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant. | Implement Plan & Policies and upgrade systems accordingly; provide suitable training to enable staff to utilize these systems optimally and correctly. | Workplace skills plan reviewed annually | n/a | Human Resource Department | Develop a workplace skills plan with an annual training report by 30th March 2018. | 1 | Collect information from departments to develop plans. | Development of workplace skills plan and annual training report. | Submission to LG Seta and implementation report. | n/a |
| To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant. | Implement Plan & Policies and upgrade systems accordingly; provide suitable training to enable staff to utilize these systems optimally and correctly. | Financial Policies adopted by Council. | n/a | Finance Department | Review 13 Financial Policies and table before Council for approval by 30 June 2018. | 13 | n/a | n/a | Workshop, Asset Management Policy, Supply chain Management policy, Fleet management policy, Contract Management policy, Credit and Debt collection Policy, Indigent Policy, Inventory policy, fruitless, wasteful and irregular expenditure policy, Budget policy, rewards, gifts and favours policy, virement policy, Investment policy, petty cash policy . | Approval by Council of reviewed policies |
| To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant. | Implement Plan & Policies and upgrade systems accordingly; provide suitable training to enable staff to utilize these systems optimally and correctly. | 9 HR Policies adopted by Council in 2016/2017 | n/a | Human Resource Department | Number of HR policies reviewed and approved by council by 31st December 2017 | 10 | Review 6 policies | Review 4 Policies and workshop Council and stakeholders on all reviewed policies. Table policies before Council for adoption. | n/a | n/a |
| To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as legally compliant | Implement Plan & Policies and upgrade systems accordingly; provide suitable training to enable staff to utilize these systems optimally and correctly. | No SPAZA policy developed for Dr. Beyers Naude Local Municipality | n/a | Town Planning | Number of SPAZA Shop policies reviewed and approved by council by 31 December 2017 | 1 | n/a | Review policy and workshop Council and Stakeholders. Table before Council for adoption | n/a | n/a |
| To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant. | Implement Plan & Policies and upgrade systems accordingly; provide suitable training to enable staff to utilize these systems optimally and correctly. | 4 quarterly SCM reports submitted to Council annually. | n/a | Supply Chain Department | Prepare Supply Chain Management Implementation Compliance through 3 quarterly reports by 30 June 2018. | 3 | n/a | 1 Quarterly SCM Report | 1 Quarterly SCM Report | 1 Quarterly SCM Report |
| To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant. | Implement Plan & Policies and upgrade systems accordingly; provide suitable training to enable staff to utilize these systems optimally and correctly. | 4 quarterly reports submitted to Council annually. | n/a | Supply Chain/Asset Department | Conduct quarterly Assets reconciliation between AR and GL. 4 quarterly reports by 30 June 2018. | 4 | Recon assets register with GL and provide a report | Recon assets register with GL and provide a report | Recon assets register with GL and provide a report | Recon assets register with GL and provide a report |
| To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant. | Implement Plan & Policies and upgrade systems accordingly; provide suitable training to enable staff to utilize these systems optimally and correctly. | 4 quarterly SCM reports submitted to Council annually. | n/a | Supply Chain Department | Develop and Monitor Contract register for all service providers and provide quarterly reports. | 3 | n/a | Contract register Report | Contract register Report | Contract register Report |
| To develop a performance management culture within the Municipality | Quarterly institutional performance reports to Council. | 2 quarterly reports submitted to Council in 2016/2017 | n/a | Municipal Manager/PMS unit | 4 quarterly SDBIP Performance reports submitted to Council by 30 June 2018, to inform Council of Institutional Performance. | 4 | 1 SDBIP Performance report submitted to Council By October 2017. | 1 SDBIP Performance report submitted to Council By January 2017. | 1 SDBIP Performance report submitted to Council By April 2017. | 1 SDBIP Performance report submitted to Council By July 2017. |
| Improved performance through effective PMS | Train staff for operation of institutional PMS | No automated PMS. Staff to be trained on automated system. | n/a | Municipal Manager/PMS unit | Number of staff trained on the performance management system by 30 June 2018. | 5 | n/a | n/a | n/a | Train all staff that entered into a performance agreement/performance plan. |
| To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant. | Implement Plan & Policies and upgrade systems accordingly; provide suitable training to enable staff to utilize these systems optimally and correctly | No council resolution report submitted to Council quarterly. | n/a | Administration Department | Monitor Council resolutions by providing 4 quarterly reports on the implementation of council resolutions. | 4 | 1 | 1 | 1 | 1 |
| To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant. | Implement Plan & Policies and upgrade systems accordingly; provide suitable training to enable staff to utilize these systems optimally and correctly. | Register updated quarterly | n/a | Corporate services | Compile a Lease Register with a list of all signed lease agreements by 30 June 2018. | 1 | Update register with all signed lease agreements | Update register with all signed lease agreements | Update register with all signed lease agreements | n/a |
| To provide sufficient operational requirements, furnish and equip the relevant offices and venues, in order to improve efficiency of all departments, their staff and the Municipality’s levels of service delivery, as well as be legally compliant. | Implement Plan & Policies and upgrade systems accordingly; provide suitable training to enable staff to utilize these systems optimally and correctly. | 1 report was submitted to EXCO during 16/17 | n/a | Human Resources Department | Report on all disciplinary hearings on a quarterly basis to EXCO. | 4 | Report on all disciplinary hearing | Report on all disciplinary hearing | Report on all disciplinary hearing | Report on all disciplinary hearing |

| LOCAL ECONOMIC DEVELOPMENT |  |  |  |  |  |  | PERFORMANCE MILESTONES |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective | Strategy | Baseline | Budget | Depart | KPI | Annual Target | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| SUSTAINABLE JOB CREATION  BEE & PARTNERSHIPS  SMME, INDUSTRIAL AND SECTOR DEVELOPMENT  SKILLS DEVELOP-MENT  MAINSTREAMING OF 2ND ECONOMY, YOUTH, DISABLED & WOMEN | Support, encourage and facilitate value-adding initiatives, programmes and projects | SMME’s trained in 2016/2017 | 84,217 | Municipal Manager/ LED Unit | Profiling and building capacity in SMMEs – 4 new SMMEs trained in (Export and Business Training) in Graaff-Reinet by 30 June 2017. | 4 | Train 1 SMME | Train 1 SMME | Train 1 SMME | Train 1 SMME |
| SUSTAINABLE JOB CREATION  BEE & PARTNERSHIPS  SMME, INDUSTRIAL AND SECTOR DEVELOPMENT  SKILLS DEVELOP-MENT  MAINSTREAMING OF 2ND ECONOMY, YOUTH, DISABLED & WOMEN | Support, encourage and facilitate value-adding initiatives, programmes and projects | 132 people employed through the EPWP labour intensive programme for 2016/2017 | 1,233,000 | Municipal Manager/LED Unit | Number of people employed through the EPWP Labour intensive programme to address high unemployment rate in Dr. Beyers Naude Local Municipality by 30 June 2018. | 200 | Quarterly reports to Council - with 25 people employed | Quarterly reports to Council - with 25 people employed | Quarterly reports to Council - with 75 people employed | Quarterly reports to Council - with 75 people employed |
| SUSTAINABLE JOB CREATION  BEE & PARTNERSHIPS  SMME, INDUSTRIAL AND SECTOR DEVELOPMENT  SKILLS DEVELOP-MENT  MAINSTREAMING OF 2ND ECONOMY, YOUTH, DISABLED & WOMEN | Support, encourage and facilitate value-adding initiatives, programmes and projects | New KPI | n/a | Municipal Manager/LED Unit | Number of labourers employed for the project: Reconstruction of Lincom and Asherville schools In Graaff-Reinet by 30 June 2018. | 100 | n/a | n/a | Selection and screening processes | Appointment of 50 labourers for Lincom reconstruction and 50 labourers for Asherville reconstruction |
| SUSTAINABLE JOB CREATION  BEE & PARTNERSHIPS  SMME, INDUSTRIAL AND SECTOR DEVELOPMENT  SKILLS DEVELOP-MENT  MAINSTREAMING OF 2ND ECONOMY, YOUTH, DISABLED & WOMEN | Support, encourage and facilitate value-adding initiatives, programmes and projects | New KPI | n/a | Municipal Manager/LED Unit | Number of SMME’s employed for the project: Reconstruction of Lincom and Asherville schools In Graaff-Reinet by 30 June 2018 | 16 | n/a | n/a | Selection and screening processes | Appointment of 16 SMME’s for the reconstruction of of Lincom and Asherville schools. |
| SUSTAINABLE JOB CREATION  BEE & PARTNERSHIPS  SMME, INDUSTRIAL AND SECTOR DEVELOPMENT  SKILLS DEVELOP-MENT  MAINSTREAMING OF 2ND ECONOMY, YOUTH, DISABLED & WOMEN | Develop LED Strategic Plan with an economic Vision for the Municipality. | No commonage plan adopted by Council. | n/a | Municipal Manager/LED Unit | Number of commonage plans developed by the 30th June 2018. | 1 | n/a | Apply for funding from SBDM. | Supply chain processes commence: advertisement and appointment of service provider. | 1 commonage plan developed. |
| SUSTAINABLE JOB CREATION  BEE & PARTNERSHIPS  SMME, INDUSTRIAL AND SECTOR DEVELOPMENT  SKILLS DEVELOP-MENT  MAINSTREAMING OF 2ND ECONOMY, YOUTH, DISABLED & WOMEN | Support, encourage and facilitate value-adding initiatives, programmes and projects | 90,000 was used to assist SMME’s within 2016/2017 | 36,728. | Municipal Manager/LED Unit | Assistance and development of SMME’s by 30 June 2018. | 5 | Identify 5 potential SMME’s to be supported. | Assist and develop 3 SMME’s | Assist and develop 2 SMME’s | Report to Council on the assistance and development of SMME’s |
| SUSTAINABLE JOB CREATION  BEE & PARTNERSHIPS  SMME, INDUSTRIAL AND SECTOR DEVELOPMENT  SKILLS DEVELOP-MENT  MAINSTREAMING OF 2ND ECONOMY, YOUTH, DISABLED & WOMEN | Develop LED Strategic Plan with an economic Vision for the Municipality. | No Tourism policy strategy by Council | n/a | Municipal Manager/LED Unit | Develop a Tourism strategy by 31st December 2017 | 1 | Develop Tourism strategy | Workshop Tourism strategy | n/a | n/a |
| SUSTAINABLE JOB CREATION  BEE & PARTNERSHIPS  SMME, INDUSTRIAL AND SECTOR DEVELOPMENT  SKILLS DEVELOP-MENT  MAINSTREAMING OF 2ND ECONOMY, YOUTH, DISABLED & WOMEN | Develop LED Strategic Plan with an economic Vision for the Municipality. | No LED strategy adopted by Council | n/a | Municipal Manager/LED Unit | Develop LED Strategy by 31st December 2017 | 1 | Develop LED strategy | Workshop LED strategy | n/a | n/a |
| Creating and enabling environment to attract investment that generates economic growth and job creation | Implement strategic LED Action and Interventions with the aim of creating networks, linkages, referral & support systems, appropriate policies, by-laws, incentives, services and infrastructure that will stimulate and facilitate LED, attract investment, encourage establishment and growth of business and industry in the Dr. Beyers Naude LM. | New KPI | 400,000 | Municipal Manager/LED Unit | Implement 2 initiatives identified by the Mohair summit by 30th June 2018. | 2 | n/a | 1. Planning and Marketing for SMME Imbizo to be held in March 2018. 2. Planning for Mohair empowerment trust. | 1. SMME Mohair Imbizo - March 2018 | 2. Ceremony for handover of contribution towards Mohair empowerment trust. |

| BACK TO BASICS – KPA – Good Governance & Public Participation |  |  |  |  |  |  | PERFORMANCE MILESTONES |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective | Strategy | Baseline | Budget | Depart | KPI | Annual Target | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| To become the best performing Municipality, in all respects. | Developing a credible Integrated Development Plan that will address the developmental needs of our Community. | 5 year credible IDP adopted by Council on 23rd May 2017. | n/a | Municipal Manager/IDP Unit | A reviewed and credible IDP for 2018/19 | 1 | (a) Prepare 2018/19 IDP & Budget Process Plan, (b) 14 x Ward Committee consultation meetings, (c) 1 x IDP RF meeting (launch), (d) Adopted IDP & Budget Process Plan. | (a) 14 x Ward-based Planning Public Participation Meetings (b) 1 x reviewed CBP Report (inclusive of Ward Development Priorities), (c) 2 x IDP SC meetings, (d) 1 x IDP RF meeting, (e) 1st Draft IDP Project Register. | (a) 2nd Draft IDP Project Register, (b) 1 x IDP SC meeting, (c) 1 x IDP RF meeting, (d) 1 x Draft 2nd Edition: 2018/19 IDP adopted by Council. | (a) 14 x Mayoral Outreach / PP meetings, (b) 1 x IDP SC meeting, (c) 1 x IDP RF meeting, (d) 1 x first review of 2017 - 2022 IDP approved by Council. |
| To become the best performing Municipality, in all respects. | Having a fully functional Council, with Standing Committees, Fora and other structures. | 3 Ordinary Council Meetings, 7 Exco Meetings, 11 Special Council Meeting 2016 - 2017 | n/a | Administration Department | Number of Meetings held in terms of year planner by 30 June 2017. (4 Ordinary Council Meetings and 4 Standing Committee meetings) | 8 | Ensure that Standing Committee meetings are held, one Ordinary Council Meeting and a Special Council meeting in terms of the year planner. Monthly Resolution Implementation Report submitted to MM | Ensure that Standing Committee meetings are held, one Ordinary Council Meeting and a Special Council meeting in terms of the year planner. Monthly Resolution Implementation Report submitted to MM | Ensure that Standing Committee meetings are held, one Ordinary Council Meeting and a Special Council meeting in terms of the year planner. Monthly Resolution Implementation Report submitted to MM | Ensure that Standing Committee meetings are held, one Ordinary Council Meeting and a Special Council meeting in terms of the year planner. Monthly Resolution Implementation Report submitted to MM |
| To become the best performing Municipality, in all respects. | Ensuring that Ward Committees have been established and are functioning properly, and that a CDW has been appointed in each Ward | No CDW’s deployed at ward level | n/a | Municipal Manager | CDW’s deployed at ward level with monthly report submission. | 12 | 3 monthly reports from each CDW. | 3 monthly reports from each CDW. | 3 monthly reports from each CDW. | 3 monthly reports from each CDW. |
| To become the best performing Municipality, in all respects. | Having a fully functional Council, with Standing Committees, Fora and other structures. | 4 MPAC meetings held 2016/2017 | n/a | Administration Department | Number of MPAC meetings to assist with oversight function until 30 June 2018. | 4 | Organise MPAC meeting | Organise MPAC meeting | Organise MPAC meeting | Organise MPAC meeting |
| To become the best performing Municipality, in all respects. | Having a fully functional Council, with Standing Committees, Fora and other structures. | 4 audit committee meetings held during 2016/2017 | n/a | Administration Department | Number of Audit Committee meetings to assist with oversight function until 30 June 2018. | 4 | Organise Audit Committee meeting | Organise Audit Committee meeting | Organise Audit Committee meeting | Organise Audit Committee meeting |
| To become the best performing Municipality, in all respects | Installing and maintaining effective and efficient communications and other systems that will improve information-sharing, enhance public participation and promote socio-economic development. | 8 LLF Meetings held 2016/2017 | n/a | Human Resources Department | Ensure that the LLF is functioning properly and fulfilling its mandate by having 6 Meetings annually | 6 | 2 Meetings | 2 Meetings | 1 Meeting | 1 Meeting |
| To become the best performing Municipality, in all respects. | Installing and maintaining effective and efficient communications and other systems that will improve information-sharing, enhance public participation and promote socio-economic development. | Quarterly reports submitted to the Municipal Manager and Council. | n/a | Municipal Manager/Communications | Implement Communication Action Plans by providing quarterly progress reports by 30th June 2018. | 4 | Improve internal communication by executing communication action plan and report progress to the Municipal Manager | Improve internal communication by executing communication action plan and report progress to the Municipal Manager | Improve internal communication by executing communication action plan and report progress to the Municipal Manager | Improve internal communication by executing communication action plan and report progress to the Municipal Manager |
| To become the best performing Municipality, in all respects | Installing and maintaining effective and efficient communications and other systems that will improve information-sharing, enhance public participation and promote socio-economic development. | 40 000 newsletter distributed during 2016/2017 | 19,500. | Municipal Manager/Communications | Number of quarterly External Newsletters distributed to stakeholders by 30th June 2018 | 60 000 | 15000 Quarterly External Newsletters distributed. | 15000 Quarterly External Newsletters distributed. | 15000 Quarterly External Newsletters distributed. | 15000 Quarterly External Newsletters distributed. |
| To become the best performing Municipality, in all respects. | Installing and maintaining effective and efficient communications and other systems that will improve information-sharing, enhance public participation and promote socio-economic development. | 4 interviews held with the Mayor in 2016/2017 | n/a | Municipal Manager/Communications | Number of Interviews Held with the Mayor and submitted to the local Newspaper (The advertiser) by 30th June 2018. | 4 | Quarterly interviews with the Mayor and submit to the Local Newspaper (The advertiser) | Quarterly interviews with the Mayor and submit to the Local Newspaper (The advertiser) | Quarterly interviews with the Mayor and submit to the Local Newspaper (The advertiser) | Quarterly interviews with the Mayor and submit to the Local Newspaper (The advertiser) |
| To become the best performing Municipality, in all respects. | Installing and maintaining effective and efficient communications and other systems that will improve information-sharing, enhance public participation and promote socio-economic development. | Housing register updated continuously | n/a | Corporate services | Maintain updated housing beneficiary list and submit to Department of Human settlement on a quarterly basis by 30th June 2018 | 4 | Updated beneficiary list and quarterly submission to the Department of Human Settlement | Updated beneficiary list and quarterly submission to the Department of Human Settlement | Updated beneficiary list and quarterly submission to the Department of Human Settlement | Updated beneficiary list and quarterly submission to the Department of Human Settlement |
| To become the best performing Municipality, in all respects. | Ensuring that Ward Committees have been established and are functioning properly, and that a CDW has been appointed in each Ward. | No CDW’s deployed at ward level | n/a | Corporate Services (ward coordinator) | Quarterly Ward Committee meetings until 30 June 2018 | 4 | Ensure quarterly ward committee meetings | Ensure quarterly ward committee meetings | Ensure quarterly ward committee meetings | Ensure quarterly ward committee meetings. |
| To become the best performing Municipality, in all respects | Providing Free Basic Services and Indigent Support. | Indigent register in place. | n/a | Finance Department | Extend the Indigent Register by registering 120 Houses by 30th June 2018. | 120 | Register 30 houses | Register 30 houses | Register 30 houses | Register 30 houses and have awareness campaigns in all wards. |
| BACK TO BASICS – KPA – Sound Financial Management |  |  |  |  |  | PERFORMANCE MILESTONES |  |  |  |  |

| Objective | Strategy | Baseline | Budget | Depart | KPI | Annual Target | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| To become a financially viable and sustainable Municipality. | The development and implementation of a Funding Strategy. | 64,460,430 | 1,085,000 AIG 5,945000 FMG | Finance Department | 100% expenditure of Municipal FMG and Audit Improvement Grant by 30th June 2018. | 100% | 15% | 30% | 70% | 100% |
| To receive a Clean Audit Opinion from the Auditor-General. | Implementation and execution of an Audit Action Plan. | Delay In submission of S71 and S52 reports in 2016/2017 | n/a | Municipal Manager | 100% Reporting compliance by submitting s71, s72 and s52d reports within legislated timeframes 30th June 2018. | 100% | 100% compliance to Financial Planner Deadlines | 100% compliance to Financial Planner Deadlines | 100% compliance to Financial Planner Deadlines | 100% compliance to Financial Planner Deadlines |
| To receive a Clean Audit Opinion from the Auditor-General. | Implementation and execution of an Audit Action Plan. | Audit Implementation plan developed for all audit findings of 2015/2016 | n/a | Municipal Manager | Improve Outcome of the AG report: Execute action plan to address previous findings by 30 June 2018. | 1 | n/a | n/a | All audit findings for 16/17 addressed in terms of audit action plan | All audit findings for 16/17 addressed in terms of audit action plan |
| To receive a Clean Audit Opinion from the Auditor-General. | Implementation and execution of an Audit Action Plan. | Verification of the completeness of the asset register conducted annually. | n/a | Supply Chain Department | Verification of the completeness of the Asset Register (Asset Register compliant to GRAP standards) | 100% | All purchases captured and updated on Asset Register | All purchases captured and updated on Asset Register and Follow up on queries of Auditor General | All purchases captured and updated on Asset Register and address audit outcomes | All purchases captured and updated on Asset Register and conduct an Annual review of the condition and useful life of assets. |
| To become a financially viable and sustainable Municipality. | Alignment of the Budget to the IDP’s Development Priorities. | 19,984,111,000 | 72,179,387 | Municipal Manager | Percentage CAPEX of budget spend by 30th June 2018. | 100% | 15% | 30% | 70% | 100% |
| To become a financially viable and sustainable Municipality. | Alignment of the Budget to the IDP’s Development Priorities. | 253,242,25.00 | 440,303,588 | Municipal Manager | Percentage OPEX of budget spend by 30th June 2018. | 80% | 30% spent | 55% spent | 75% spent | 80% spent |
| To adopt a realistic, credible and funded Annual Budget | Alignment of the Budget to the IDP’s Development Priorities. | 2017/2018 Budget approved | n/a | Municipal Manager | 2018//2019 Budget approved by Council by 31 May 2018. | 1 | Process Plan adopted | Budget priorities developed | Draft by 30 March 2018. | Approved by Council on the 31st May 2018. |
| To become a financially viable and sustainable Municipality. | Implementation and execution of the Financial Recovery Plan – robust plans for the repayment of debt and/or maintain a healthy level of cash reserves and assets in order to meet unexpected costs. | 67% Collection rate 2016/2017 | n/a | Finance Department | Improve collection rate on service debtors to address cash flow constraints by 30th June 2018 (Service debtors/service debt collected) | 80% | 25% | 50% | 70% | 80% |
| To become a financially viable and sustainable Municipality. | Implementation and execution of the Financial Recovery Plan – robust plans for the repayment of debt and/or maintain a healthy level of cash reserves and assets in order to meet unexpected costs. | Financial recovery plan developed in 16/17 with outer year targets | n/a | Finance Department | Financial recovery plan implemented and monitored by submissions quarterly to EXCO by 30th June 2018. | 4 | Ensure compliance with Financial recovery plan deadlines by submitting implementation progress report quarterly to EXCO | Ensure compliance with Financial recovery plan deadlines by submitting implementation progress report quarterly to EXCO | Ensure compliance with Financial recovery plan deadlines by submitting implementation progress report quarterly to EXCO | Ensure compliance with Financial recovery plan deadlines by submitting implementation progress report quarterly to EXCO |
| To become a financially viable and sustainable Municipality. | Stringent implementation and execution of the Municipality’s Credit Control & Debt Collection Policy. |  | n/a | Finance Department | Effective control over collection of property rates: by 30 June 2018. Property rates collected/ property rate debtors. | Ensure average 80% recovery rate of property rates billed by 30 June 2018. | Ensure effective recovery of property rates 5% | Ensure effective recovery of property rates 40% | Ensure effective recovery of property rates 60% | Ensure effective recovery of property rates 80% |
| To become the best performing Municipality, in all respects. | Implementation and execution of the Financial Recovery Plan – robust plans for the repayment of debt and/or maintain a healthy level of cash reserves and assets in order to meet unexpected costs | 7 appointed | 770,000. | Finance Department | Number of interns appointed in Finance Department by 30 June 2018. | 7 | Appoint interns | Appoint interns | Appoint interns | Appoint interns |