## Evaluation Report
Performance Evaluation Report
EC101 Dr. Beyers Naude Local Municipality
Q2(Oct-Dec)
Output as per support plan | Output achieved | Allocation as per Support Plan | Allocation spent to date | Allocation still to be spent | Reasons for non achievement of output | Remedial Measures to be implemented | Date when output will be achieved
Establishment of a Budget and Treasury Office (BTO) with positions filled by appropriately qualified personnel |  | 1810000 |  | 1810000
Appointment of atleast 5 interns | Yes | 700000 | 143042.43 | 556957.57
Acquisition, upgrade and maintenance of financial management systems to produce multi- year budgets, in-year reports, Service Delivery and Budget Implementation Plans, Annual Financial Statements, annual reports and automated financial management practices including the municipal Standard Chart of Accounts |  | 750000 | 297107.82 | 452892.18
Support the training of municipal officials in financial management towards attaining the minimum competencies |  | 700000 |  | 700000
Preparation and timely submission of Annual Financial Statements for audits |  | 1000000 |  | 1000000
Implementation of financial management reforms and address shortcomings identified in the Financial Management Capability Maturity Model (FMCMM) Assessment report |  | 500000 |  | 500000
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| Signature | Date
Municipal Manager
Chief Financial Officer
Note on A3: Select a Quarter from drop down list

## Cash Flow Projection
Dr. Beyers Naude Local Municipality Cash Flow Projection
|  | Quarter 1 |  |  | Q2 |  |  | Q3 |  |  | Q4
Output as per support plan | Allocation still to be spent | July | August | September | October | November | December | January | February | March | April | May | June | Balance Outstanding
Establishment of a Budget and Treasury Office (BTO) with positions filled by appropriately qualified personnel | 1810000 | Quarter 1 July: 0; Quarter 1 August: 0; Quarter 1 September: 0; Q2 October: 0; Q2 November: 0; Q2 December: 0 | 1810000
Appointment of atleast 5 interns | 556957.57 | Quarter 1 July: 31452; Quarter 1 August: 33768; Quarter 1 September: 30204; Q2 October: 23814; Q2 November: 0; Q2 December: 23804.43 | 413915.14
Acquisition, upgrade and maintenance of financial management systems to produce multi- year budgets, in-year reports, Service Delivery and Budget Implementation Plans, Annual Financial Statements, annual reports and automated financial management practices including the municipal Standard Chart of Accounts | 452892.18 | Quarter 1 July: 6582; Quarter 1 August: 22904; Quarter 1 September: 9690; Q2 October: 62832; Q2 November: 169185.45; Q2 December: 25914.37 | 155784.36
Support the training of municipal officials in financial management towards attaining the minimum competencies | 700000 | Quarter 1 July: 0; Quarter 1 August: 0; Quarter 1 September: 0; Q2 October: 0; Q2 November: 0; Q2 December: 0 | 700000
Preparation and timely submission of Annual Financial Statements for audits | 1000000 | Quarter 1 July: 0; Quarter 1 August: 0; Quarter 1 September: 0; Q2 October: 0; Q2 November: 0; Q2 December: 0 | 1000000
Implementation of financial management reforms and address shortcomings identified in the Financial Management Capability Maturity Model (FMCMM) Assessment report | 500000 | Quarter 1 July: 0; Quarter 1 August: 0; Quarter 1 September: 0; Q2 October: 0; Q2 November: 0; Q2 December: 0 | 500000
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
| Signature | Quarter 1 July: Date
Municipal Manager
Chief Financial Officer